## Fee Breakdown
		Approach (A)		Approach (B)		Approach (C)		Estimated Duration
%	Phase	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs
5.00%	Phase 1: / Programming	0.4%	$531	0.5%	$594	0.5%	$656	1.0 wks
20.00%	Phase 2: / Schematic Design	1.7%	$2,125	1.9%	$2,375	2.1%	$2,625	2.0 wks
20.00%	Phase 3: / Design Development	1.7%	$2,125	1.9%	$2,375	2.1%	$2,625	2.0 wks
30.00%	Phase 4: / Construction Documents	2.6%	$3,188	2.9%	$3,563	3.2%	$3,938	3.0 wks
5.00%	Phase 5: / Bidding & Contract Negotiation	0.4%	$531	0.5%	$594	0.5%	$656	1.0 wks
20.00%	Phase 6: / Construction Administration	1.7%	$2,125	1.9%	$2,375	2.1%	$2,625	n/a
100.00%	All Phases	8.5%	$10,625	9.5%	$11,875	10.5%	$13,125
Assuming a Construction Cost =								$125,000

## Hour Breakdown
Square Footage	10,000 SF
Estimated Dollar per Square Footage	300 $/SF
Total Estimated Construction Costs	$125,000.00
Architecture/Eng Fees - Percentage of Construction	8.5%
Architecture & Engineering Fees	$10,625.00

Average ($/Hr) Billing Rate	$55.00
		Each Phase	Cumulative	Hours dedicated to each phase	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people
Phase 1 - Programming	5.00%	$531.25	$531.25	10 hrs	0.5 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks	0.0 wks
Phase 2 - Schematic	20.00%	$2,125.00	$2,656.25	39 hrs	1.9 wks	1.3 wks	1.0 wks	0.6 wks	0.5 wks	0.2 wks
Phase 3 - Design Development	20.00%	$2,125.00	$4,781.25	39 hrs	1.9 wks	1.3 wks	1.0 wks	0.6 wks	0.5 wks	0.2 wks
Phase 4 - Construction Documents	30.00%	$3,187.50	$7,968.75	58 hrs	2.9 wks	1.9 wks	1.4 wks	1.0 wks	0.7 wks	0.3 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$531.25	$8,500.00	10 hrs	0.5 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks	0.0 wks
Phase 6 - Construction Administration	20.00%	$2,125.00	$10,625.00	39 hrs	1.9 wks	1.3 wks	1.0 wks	0.6 wks	0.5 wks	0.2 wks
	100.00%	$10,625.00	$10,625.00	193 hrs	9.7 wks	6.4 wks	4.8 wks	3.2 wks	2.4 wks	1.0 wks

## Hourly Rates
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	A Rough Estimated Percentage of Overall Construction Costs	If Approach (A) is used
Architecture (OpeningDesign)				82.4%	7.0%	$8,750.00
Level 1	$85/HR	$95/HR	$105/HR
Level 2	$70/HR	$80/HR	$90/HR
Level 3	$60/HR	$70/HR	$80/HR
Civil Engineer (Quam Engineering)				0.0%	0.0%	$0.00
Level 1	$125/HR	$135/HR	$145/HR
Level 2	$110/HR	$120/HR	$130/HR
Level 3	$100/HR	$110/HR	$120/HR
Structural Engineer (Ntrive)				11.8%	1.0%	$1,250.00
Level 1	$150/HR	$160/HR	$170/HR
Level 2	$100/HR	$110/HR	$120/HR
Level 3	$90/HR	$100/HR	$110/HR
Mechanical Engineer (Desapex)				0.0%	0.0%	$0.00
Level 1	$45/HR	$55/HR	$65/HR
Level 2	$35/HR	$45/HR	$55/HR
Level 3	$35/HR	$45/HR	$55/HR
Electrical Engineer				0.0%	0.0%	$0.00
Level 1	$150/HR	$160/HR	$170/HR
Level 2	$100/HR	$110/HR	$120/HR
Level 3	$90/HR	$100/HR	$110/HR
Plumbing Engineer (Zenteno Solutions)				0.0%	0.0%	$0.00
Level 1	$70/HR	$80/HR	$90/HR
Level 2	$60/HR	$70/HR	$80/HR
Level 3	$50/HR	$60/HR	$70/HR
LEED Consulting (OpeningDesign)				0.0%	0.0%	$0.00
Level 1	$85/HR	$95/HR	$105/HR
Level 2	$70/HR	$80/HR	$90/HR
Level 3	$60/HR	$70/HR	$80/HR
Virtual Reality Experience (Arch Virtual)	-	-	-	0.0%	0.0%	$0.00
Potential Additional Consultants				5.9%	0.5%	$625.00
• Lighting
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				100.0%	8.5%	$10,625.00