## Fee Breakdown
		Approach (A)		Approach (B)		Approach (C)		Estimated Duration
%	Phase	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs
10.00%	Phase 1: / Pre-Design & Programming	0.4%	$39,000	0.5%	$48,750	0.6%	$58,500	47.0 wks
20.00%	Phase 2: / Schematic Design	0.8%	$78,000	1.0%	$97,500	1.2%	$117,000	93.0 wks
15.00%	Phase 3: / Design Development	0.6%	$58,500	0.8%	$73,125	0.9%	$87,750	70.0 wks
30.00%	Phase 4: / Construction Documents	1.2%	$117,000	1.5%	$146,250	1.8%	$175,500	139.0 wks
5.00%	Phase 5: / Bidding & Contract Negotiation	0.2%	$19,500	0.3%	$24,375	0.3%	$29,250	24.0 wks
20.00%	Phase 6: / Construction Administration	0.8%	$78,000	1.0%	$97,500	1.2%	$117,000	n/a
100.00%	All Phases	4.0%	$390,000	5.0%	$487,500	6.0%	$585,000
Assuming a Construction Cost =							$9,750,000

## Hour Breakdown
Square Footage	75,000 SF
How Many Dwelling Units	56 units
Estimated Dollar per Square Footage	130 $/SF
Total Estimated Construction Costs	$9,750,000.00
Architecture Fees - Percentage of Construction	4.0%
Architecture Fees Only	$390,000.00
Architecture Fees – Cost per SF	5.2 $/SF
Architecture Fees – Cost per Unit	$6964/unit

Architecture & Eng Fees - Percentage of Construction	5.7%
Architecture & Engineering Fees	$550,875.00
Architecture & Engineering Fees – Cost per SF	7.3 $/SF
Architecture & Engineering Fees – Cost per Unit	$9837/unit

Man Hour Breakdown – Architecture Only
Average ($/Hr) Billing Rate	$65.00
		Each Phase	Cumulative	Hours dedicated to each phase	Weeks – 1/3 person	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1 - Programming	10.00%	$39,000.00	$39,000.00	600 hrs	46.2 wks	30.0 wks	20.0 wks	15.0 wks	10.0 wks	7.5 wks	6.0 wks	5.0 wks
Phase 2 - Schematic	20.00%	$78,000.00	$117,000.00	1,200 hrs	92.3 wks	60.0 wks	40.0 wks	30.0 wks	20.0 wks	15.0 wks	12.0 wks	10.0 wks
Phase 3 - Design Development	15.00%	$58,500.00	$175,500.00	900 hrs	69.2 wks	45.0 wks	30.0 wks	22.5 wks	15.0 wks	11.3 wks	9.0 wks	7.5 wks
Phase 4 - Construction Documents	30.00%	$117,000.00	$292,500.00	1,800 hrs	138.5 wks	90.0 wks	60.0 wks	45.0 wks	30.0 wks	22.5 wks	18.0 wks	15.0 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$19,500.00	$312,000.00	300 hrs	23.1 wks	15.0 wks	10.0 wks	7.5 wks	5.0 wks	3.8 wks	3.0 wks	2.5 wks
Phase 6 - Construction Administration	20.00%	$78,000.00	$390,000.00	1,200 hrs	92.3 wks	60.0 wks	40.0 wks	30.0 wks	20.0 wks	15.0 wks	12.0 wks	10.0 wks
	100.00%	$390,000.00	$390,000.00	6,000 hrs	461.5 wks	300.0 wks	200.0 wks	150.0 wks	100.0 wks	75.0 wks	60.0 wks	50.0 wks

## Hourly Rates
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	A Rough Estimated Percentage of Overall Construction Costs		Percentage of Architectural Fees	Cost with Approach (A)		Cost per SF	Cost per Unit
Architecture (OpeningDesign)				70.8%	4.00%		100.0%	$390,000		5.2 $/SF	6,964 $/SF
Skill Level 1	$75/HR	$85/HR	$95/HR
Skill Level 2	$65/HR	$75/HR	$85/HR
Skill Level 3	$45/HR	$55/HR	$65/HR
Civil Engineer (Quam Engineering)				7.1%	0.40%		10.0%	$39,000		.5 $/SF	696 $/SF
Skill Level 1	$125/HR	$135/HR	$145/HR
Skill Level 2	$110/HR	$120/HR	$130/HR
Skill Level 3	$100/HR	$110/HR	$120/HR
Structural Engineer				8.8%	0.50%		12.5%	$48,750		.7 $/SF	871 $/SF
Skill Level 1	$150/HR	$160/HR	$170/HR
Skill Level 2	$120/HR	$130/HR	$140/HR
Skill Level 3	$100/HR	$110/HR	$120/HR
Mechanical Engineer (Desapex)				3.5%	0.20%	0.60%	5.0%	$19,500	$58,500	.3 $/SF	348 $/SF
Skill Level 1	$45/HR	$55/HR	$65/HR
Skill Level 2	$35/HR	$45/HR	$55/HR
Skill Level 3	$35/HR	$45/HR	$55/HR
Electrical Engineer (OpeningDesign)				3.5%	0.20%		5.0%	$19,500		.3 $/SF	348 $/SF
Skill Level 1	$150/HR	$160/HR	$170/HR
Skill Level 2	$100/HR	$110/HR	$120/HR
Skill Level 3	$90/HR	$100/HR	$110/HR
Plumbing Engineer (Zenteno Solutions)				3.5%	0.20%		5.0%	$19,500		.3 $/SF	348 $/SF
Skill Level 1	$70/HR	$80/HR	$90/HR
Skill Level 2	$60/HR	$70/HR	$80/HR
Skill Level 3	$50/HR	$60/HR	$70/HR
LEED Consulting (OpeningDesign)				0.0%	0.00%		0.0%	$0		.0 $/SF	$/SF
Skill Level 1	$85/HR	$95/HR	$105/HR
Skill Level 2	$70/HR	$80/HR	$90/HR
Skill Level 3	$60/HR	$70/HR	$80/HR
Potential Additional Consultants				2.7%	0.15%		3.8%	$14,625		.2 $/SF	261 $/SF
• Lighting
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				100.0%	5.7%			$550,875		7.3 $/SF	9,837.1 $/SF