## Fee Breakdown
		Approach (A)		Approach (B)		Approach (C)		Estimated Duration
%	Phase	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Cost Per SF
10.00%	Phase 1: / Pre-Design & Programming	0.8%	$4,696	0.9%	$5,255	1.0%	$5,814	2.0 wks	$1.09
20.00%	Phase 2: / Schematic Design	1.7%	$9,391	1.9%	$10,509	2.1%	$11,627	4.0 wks	$2.18
15.00%	Phase 3: / Design Development	1.3%	$7,043	1.4%	$7,882	1.6%	$8,720	3.0 wks	$1.64
30.00%	Phase 4: / Construction Documents	2.5%	$14,087	2.8%	$15,764	3.1%	$17,441	5.0 wks	$3.28
5.00%	Phase 5: / Bidding & Contract Negotiation	0.4%	$2,348	0.5%	$2,627	0.5%	$2,907	1.0 wks	$0.55
20.00%	Phase 6: / Construction Administration	1.7%	$9,391	1.9%	$10,509	2.1%	$11,627	n/a	$2.18
100.00%	All Phases	8.4%	$46,956	9.4%	$52,546	10.4%	$58,136	15.0 wks (Design Only)	$10.92
Assuming a Construction Cost =							$559,000

	Disciplines	Approach (A)		Approach (B)		Approach (C)
	Architectural Only	6.50%	$36,335	7.27%	$40,661	8.05%	$44,986		$8.45
	Civil Engineering Only	0.0%	$0	0.00%	$0	0.00%	$0		$0.00
	Structural Engineering Only	0.3%	$1,677	0.34%	$1,877	0.37%	$2,076		$0.39
	Mechanical Engineering Only	0.7%	$3,913	0.78%	$4,379	0.87%	$4,845		$0.91
	Electrical Engineering Only	0.00%	$0	0.00%	$0	0.00%	$0		$0.00
	Plumbing Engineering Only	0.70%	$3,913	0.78%	$4,379	0.87%	$4,845		$0.91
	Other Minor Consultants	0.20%	$1,118	0.22%	$1,251	0.25%	$1,384		$0.26
	Totals	8.4%	$46,956	9.4%	$52,546	10.4%	$58,136		$10.92

## Hour Breakdown
Square Footage	4,300 SF
How Many Dwelling Units	56 units
Estimated Dollar per Square Footage	130 $/SF
Total Estimated Construction Costs	$559,000.00
Architecture Fees - Percentage of Construction	6.5%
Architecture Fees Only	$36,335.00
Architecture Fees – Cost per SF	8.5 $/SF
Architecture Fees – Cost per Unit	$649/unit

Architecture & Eng Fees - Percentage of Construction	8.4%
Architecture & Engineering Fees	$46,956.00
Architecture & Engineering Fees – Cost per SF	10.9 $/SF
Architecture & Engineering Fees – Cost per Unit	$839/unit

Man Hour Breakdown – Architecture Only
Average ($/Hr) Billing Rate	$75.00
		% of Construction	Each Phase	Cumulative	Cost per SF	Cost per SF Cumulative	Hours dedicated to each phase	Weeks – 1/3 person	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1 - Programming	10.00%	0.65%	$3,633.50	$3,633.50	$0.85	$0.85	48 hrs	3.7 wks	2.4 wks	1.6 wks	1.2 wks	0.8 wks	0.6 wks	0.5 wks	0.4 wks
Phase 2 - Schematic	20.00%	1.30%	$7,267.00	$10,900.50	$1.69	$2.54	97 hrs	7.5 wks	4.8 wks	3.2 wks	2.4 wks	1.6 wks	1.2 wks	1.0 wks	0.8 wks
Phase 3 - Design Development	15.00%	0.98%	$5,450.25	$16,350.75	$1.27	$3.80	73 hrs	5.6 wks	3.6 wks	2.4 wks	1.8 wks	1.2 wks	0.9 wks	0.7 wks	0.6 wks
Phase 4 - Construction Documents	30.00%	1.95%	$10,900.50	$27,251.25	$2.54	$6.34	145 hrs	11.2 wks	7.3 wks	4.8 wks	3.6 wks	2.4 wks	1.8 wks	1.5 wks	1.2 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	0.33%	$1,816.75	$29,068.00	$0.42	$6.76	24 hrs	1.9 wks	1.2 wks	0.8 wks	0.6 wks	0.4 wks	0.3 wks	0.2 wks	0.2 wks
Phase 6 - Construction Administration	20.00%	1.30%	$7,267.00	$36,335.00	$1.69	$8.45	97 hrs	7.5 wks	4.8 wks	3.2 wks	2.4 wks	1.6 wks	1.2 wks	1.0 wks	0.8 wks
	100.00%	6.50%	$36,335.00	$36,335.00	$8.45	$8.45	484 hrs	37.3 wks	24.2 wks	16.1 wks	12.1 wks	8.1 wks	6.1 wks	4.8 wks	4.0 wks
						9.3 months	6.1 months	4 months	3 months	2 months	1.5 months	1.2 months	1 months

## Hourly Rates
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	A Rough Estimated Percentage of Overall Construction Costs		Percentage of Architectural Fees	Cost with Approach (A)		Cost per SF	Cost per Unit
Architecture				77.4%	6.50%		100.0%	$36,335		8.5 $/SF	649 $/SF
Skill Level 1	$75/HR	$85/HR	$95/HR
Skill Level 2	$65/HR	$75/HR	$85/HR
Skill Level 3	$45/HR	$55/HR	$65/HR
Civil Engineer (Quam Engineering)				0.0%	0.00%		0.0%	$0		.0 $/SF	$/SF
Skill Level 1	$125/HR	$135/HR	$145/HR
Skill Level 2	$110/HR	$120/HR	$130/HR
Skill Level 3	$100/HR	$110/HR	$120/HR
Structural Engineer				3.6%	0.30%		4.6%	$1,677		.4 $/SF	30 $/SF
Skill Level 1	$150/HR	$160/HR	$170/HR
Skill Level 2	$120/HR	$130/HR	$140/HR
Skill Level 3	$100/HR	$110/HR	$120/HR
Mechanical Engineer				8.3%	0.70%	1.40%	10.8%	$3,913	$7,826	.9 $/SF	70 $/SF
Skill Level 1	$80/HR	$90/HR	$100/HR
Skill Level 2	$70/HR	$80/HR	$90/HR
Skill Level 3	$60/HR	$70/HR	$80/HR
Electrical Engineer				0.0%	0.00%		0.0%	$0		.0 $/SF	$/SF
Skill Level 1	$150/HR	$160/HR	$170/HR
Skill Level 2	$100/HR	$110/HR	$120/HR
Skill Level 3	$90/HR	$100/HR	$110/HR
Plumbing Engineer				8.3%	0.70%		10.8%	$3,913		.9 $/SF	70 $/SF
Skill Level 1	$80/HR	$90/HR	$100/HR
Skill Level 2	$70/HR	$80/HR	$90/HR
Skill Level 3	$60/HR	$70/HR	$80/HR
LEED Consulting (OpeningDesign)				0.0%	0.00%		0.0%	$0		.0 $/SF	$/SF
Skill Level 1	$85/HR	$95/HR	$105/HR
Skill Level 2	$70/HR	$80/HR	$90/HR
Skill Level 3	$60/HR	$70/HR	$80/HR
Potential Additional Consultants				2.4%	0.20%		3.1%	$1,118		.3 $/SF	20 $/SF
• Lighting
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				100.0%	8.4%			$46,956		10.9 $/SF	838.5 $/SF

## Details
Start	$190
Number of Details	5
Increments	$20

	Cost Per Detail			Total
Approach A	$190	-	$210	$950	-	$1,050
Approach B	$230	-	$250	$1,150	-	$1,250
Approach C	$270	-	$290	$1,350	-	$1,450