## Splash
License: / This document, like most OpeningDesign's projects, is open source (Attribution-ShareAlike 4.0 International--CC BY-SA 4.0)--freely available to any party, for any use, assuming the terms such as Attribution and ShareAlike are honored.

## Hour Breakdown
Square Footage	3,200 SF
How Many Dwelling Units	71 units
Estimated Dollar per Square Footage	100 $/SF
Total Estimated Construction Costs	$320,000.00
Architecture Fees - Percentage of Construction	5.5%
Architecture Fees Only	$17,600.00
Architecture Fees – Cost per SF	5.5 $/SF
Architecture Fees – Cost per Unit	$248/unit

Architecture & Eng Fees - Percentage of Construction	5.5%
Architecture & Engineering Fees	$17,600.00
Architecture & Engineering Fees – Cost per SF	5.5 $/SF
Architecture & Engineering Fees – Cost per Unit	$248/unit

Man Hour Breakdown – Architecture Only
Average ($/Hr) Billing Rate	$75.00
		% of Construction	Each Phase	Cumulative	Cost per SF	Cost per SF Cumulative	Hours dedicated to each phase	Weeks – ¼ person	Weeks – 1/3 person	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1 - Programming	10.00%	0.55%	$1,760.00	$1,760.00	$0.55	$0.55	23 hrs	2.3 wks	1.8 wks	1.2 wks	0.8 wks	0.6 wks	0.4 wks	0.3 wks	0.2 wks	0.2 wks
Phase 2 - Schematic	25.00%	1.38%	$4,400.00	$6,160.00	$1.38	$1.93	59 hrs	5.9 wks	4.5 wks	2.9 wks	2.0 wks	1.5 wks	1.0 wks	0.7 wks	0.6 wks	0.5 wks
Phase 3 - Design Development	20.00%	1.10%	$3,520.00	$9,680.00	$1.10	$3.03	47 hrs	4.7 wks	3.6 wks	2.3 wks	1.6 wks	1.2 wks	0.8 wks	0.6 wks	0.5 wks	0.4 wks
Phase 4 - Construction Documents	20.00%	1.10%	$3,520.00	$13,200.00	$1.10	$4.13	47 hrs	4.7 wks	3.6 wks	2.3 wks	1.6 wks	1.2 wks	0.8 wks	0.6 wks	0.5 wks	0.4 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	0.28%	$880.00	$14,080.00	$0.28	$4.40	12 hrs	1.2 wks	0.9 wks	0.6 wks	0.4 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks
Phase 6 - Construction Administration	20.00%	1.10%	$3,520.00	$17,600.00	$1.10	$5.50	47 hrs	4.7 wks	3.6 wks	2.3 wks	1.6 wks	1.2 wks	0.8 wks	0.6 wks	0.5 wks	0.4 wks
	100.00%	5.50%	$17,600.00	$17,600.00	$5.50	$5.50	235 hrs	23.5 wks	18.1 wks	11.7 wks	7.8 wks	5.9 wks	3.9 wks	2.9 wks	2.3 wks	2.0 wks
						5.9 months	4.5 months	2.9 months	2 months	1.5 months	1 months	.7 months	.6 months	.5 months

## Fee Breakdown
%	Phase	Approach (A)		Estimated Duration	Approach (B)			Approach (C)				Increment Percentage	1.00%
		Rough % of Const. Costs	Not-To-Exceed	Estimated Duration	Rough % of Const. Costs	Not-To-Exceed	Estimated Duration	Rough % of Const. Costs	Not-To-Exceed	Estimated Duration	Cost Per SF	Time Increment	1.1
20.00%	Phase 1: / Pre-Design & Programming	1.1%	$3,520	2.0 wks	1.3%	$4,160	2.6 wks	1.5%	$4,800	3.3 wks	$1.10
15.00%	Phase 2: / Schematic Design	0.8%	$2,640	3.0 wks	1.0%	$3,120	3.9 wks	1.1%	$3,600	5.0 wks	$0.83
20.00%	Phase 3: / Design Development	1.1%	$3,520	3.0 wks	1.3%	$4,160	3.9 wks	1.5%	$4,800	5.0 wks	$1.10
20.00%	Phase 4: / Construction Documents	1.1%	$3,520	3.0 wks	1.3%	$4,160	3.9 wks	1.5%	$4,800	5.0 wks	$1.10
5.00%	Phase 5: / Bidding & Contract Negotiation	0.3%	$880	1.0 wks	0.3%	$1,040	1.3 wks	0.4%	$1,200	1.7 wks	$0.28
20.00%	Phase 6: / Construction Administration	1.1%	$3,520	n/a	1.3%	$4,160	n/a	1.5%	$4,800	n/a	$1.10
100.00%	All Phases	5.5%	$17,600	12.0 wks	6.50%	$20,800	15.6 wks	7.50%	$24,000	19.8 wks	$5.50
Assuming a Construction Cost, please see note below =										$320,000

	Disciplines	Approach (A)			Approach (B)			Approach (C)
	Architecture	5.50%	$17,600		6.50%	$20,800		7.50%	$24,000
	Structural Engineer	0.0%	$0		0.00%	$0		0.00%	$0
	Civil Engineer	0.0%	$0		0.00%	$0		0.00%	$0
	Mechanical Engineer	0.0%	$0		0.00%	$0		0.00%	$0
	Electrical Engineer	0.00%	$0		0.00%	$0		0.00%	$0
	Plumbing Engineer	0.00%	$0		0.00%	$0		0.00%	$0
	Lighting	0.00%	$0		0.00%	$0		0.00%	$0
	Potential Additional Consultants	0.00%	$0		0.00%	$0		0.00%	$0
	Totals	5.5%	$17,600		6.5%	$20,800		7.5%	$24,000

## Hourly Rates
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	Cost with Approach (A)	Cost with Approach (B)	Cost with Approach (C)	A Rough Estimated Percentage of Overall Construction Costs	Percentage of Architectural Fees	Cost per SF	Cost per Unit
Architecture				100%	$17,600	$20,800	$24,000	5.50%	100.0%	5.5 $/SF	248 $/SF
Principal	$75/HR	$85/HR	$115/HR
Project Architect	$65/HR	$75/HR	$105/HR
Intern	$55/HR	$65/HR	$95/HR
Structural Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$160/HR	$170/HR	$180/HR
Engineer II	$135/HR	$145/HR	$155/HR
Engineer I	$125/HR	$135/HR	$145/HR
Civil Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$135/HR	$145/HR	$155/HR
Engineer II	$120/HR	$130/HR	$140/HR
Engineer I	$100/HR	$110/HR	$120/HR
Mechanical Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Electrical Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$150/HR	$160/HR	$170/HR
Engineer II	$100/HR	$110/HR	$120/HR
Engineer I	$90/HR	$100/HR	$110/HR
Plumbing Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Lighting				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Skill Level 1	$100/HR	$110/HR	$120/HR
Skill Level 2	$90/HR	$100/HR	$110/HR
Skill Level 3	$80/HR	$90/HR	$100/HR

Potential Additional Consultants				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
• Building Envelope Consultant
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				100%	$17,600	$20,800	$24,000	5.5%		5.5 $/SF	247.9 $/SF

## Details
Start	$300
Number of Details	58
Increments	$20

	Cost Per Detail			Total
Approach A	$300	-	$320	$17,400	-	$18,560
Approach B	$340	-	$360	$19,720	-	$20,880
Approach C	$380	-	$400	$22,040	-	$23,200