## Fee Breakdown
		Approach (A)		Approach (B)		Approach (C)		Estimated Duration
%	Phase	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs
5.00%	Phase 1: / Programming	0.7%	$16,500	0.7%	$17,750	0.8%	$19,000	3.0 wks
20.00%	Phase 2: / Schematic Design	2.6%	$66,000	2.8%	$71,000	3.0%	$76,000	10.0 wks
20.00%	Phase 3: / Design Development	2.6%	$66,000	2.8%	$71,000	3.0%	$76,000	10.0 wks
30.00%	Phase 4: / Construction Documents	4.0%	$99,000	4.3%	$106,500	4.6%	$114,000	15.0 wks
5.00%	Phase 5: / Bidding & Contract Negotiation	0.7%	$16,500	0.7%	$17,750	0.8%	$19,000	3.0 wks
20.00%	Phase 6: / Construction Administration	2.6%	$66,000	2.8%	$71,000	3.0%	$76,000	n/a
100.00%	All Phases	13.2%	$330,000	14.2%	$355,000	15.2%	$380,000
Assuming a Construction Cost =							$2,500,000

## Hour Breakdown
Square Footage	10,000 SF
Estimated Dollar per Square Footage	250 $/SF
Total Estimated Construction Costs	$2,500,000.00
Architecture/Eng Fees - Percentage of Construction	13.2%
Architecture & Engineering Fees	$330,000.00

Average ($/Hr) Billing Rate	$55.00
		Each Phase	Cumulative	Hours dedicated to each phase	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1 - Programming	5.00%	$16,500.00	$16,500.00	300 hrs	15.0 wks	10.0 wks	7.5 wks	5.0 wks	3.8 wks	3.0 wks	2.5 wks
Phase 2 - Schematic	20.00%	$66,000.00	$82,500.00	1,200 hrs	60.0 wks	40.0 wks	30.0 wks	20.0 wks	15.0 wks	12.0 wks	10.0 wks
Phase 3 - Design Development	20.00%	$66,000.00	$148,500.00	1,200 hrs	60.0 wks	40.0 wks	30.0 wks	20.0 wks	15.0 wks	12.0 wks	10.0 wks
Phase 4 - Construction Documents	30.00%	$99,000.00	$247,500.00	1,800 hrs	90.0 wks	60.0 wks	45.0 wks	30.0 wks	22.5 wks	18.0 wks	15.0 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$16,500.00	$264,000.00	300 hrs	15.0 wks	10.0 wks	7.5 wks	5.0 wks	3.8 wks	3.0 wks	2.5 wks
Phase 6 - Construction Administration	20.00%	$66,000.00	$330,000.00	1,200 hrs	60.0 wks	40.0 wks	30.0 wks	20.0 wks	15.0 wks	12.0 wks	10.0 wks
	100.00%	$330,000.00	$330,000.00	6,000 hrs	300.0 wks	200.0 wks	150.0 wks	100.0 wks	75.0 wks	60.0 wks	50.0 wks

## Hourly Rates
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	A Rough Estimated Percentage of Overall Construction Costs	Not-to-Exceed Fee if Approach (A) is used
Architecture (OpeningDesign)				56.8%	7.5%	$187,500.00
Level 1	$85/HR	$95/HR	$105/HR
Level 2	$70/HR	$80/HR	$90/HR
Level 3	$60/HR	$70/HR	$80/HR
Civil Engineer (Quam Engineering)				6.1%	0.8%	$20,000.00
Level 1	$125/HR	$135/HR	$145/HR
Level 2	$110/HR	$120/HR	$130/HR
Level 3	$100/HR	$110/HR	$120/HR
Structural Engineer (Ntrive)				6.1%	0.8%	$20,000.00
Level 1	$150/HR	$160/HR	$170/HR
Level 2	$100/HR	$110/HR	$120/HR
Level 3	$90/HR	$100/HR	$110/HR
Mechanical Engineer (Desapex)				3.8%	0.5%	$12,500.00
Level 1	$45/HR	$55/HR	$65/HR
Level 2	$35/HR	$45/HR	$55/HR
Level 3	$35/HR	$45/HR	$55/HR
Electrical Engineer (OpeningDesign)				3.0%	0.4%	$10,000.00
Level 1	$150/HR	$160/HR	$170/HR
Level 2	$100/HR	$110/HR	$120/HR
Level 3	$90/HR	$100/HR	$110/HR
Plumbing Engineer (Zenteno Solutions)				3.8%	0.5%	$12,500.00
Level 1	$70/HR	$80/HR	$90/HR
Level 2	$60/HR	$70/HR	$80/HR
Level 3	$50/HR	$60/HR	$70/HR
LEED Consulting (OpeningDesign)				9.1%	1.2%	$30,000.00
Level 1	$85/HR	$95/HR	$105/HR
Level 2	$70/HR	$80/HR	$90/HR
Level 3	$60/HR	$70/HR	$80/HR
Virtual Reality Experience (Arch Virtual)	-	-	-	7.6%	1.0%	$25,000.00
Potential Additional Consultants				3.8%	0.5%	$12,500.00
• Lighting
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				100.0%	13.2%	$330,000.00