## Splash
License: / This document, like most OpeningDesign's projects, is open source (Attribution-ShareAlike 4.0 International--CC BY-SA 4.0)--freely available to any party, for any use, assuming the terms such as Attribution and ShareAlike are honored.

## Hour Breakdown
Square Footage	2,300 SF
How Many Dwelling Units	71 units
Estimated Dollar per Square Footage	25 $/SF
Total Estimated Construction Costs	$57,500.00
Architecture Fees - Percentage of Construction	5.0%
Architecture Fees Only	$2,875.00
Architecture Fees – Cost per SF	1.3 $/SF
Architecture Fees – Cost per Unit	$40/unit

Architecture & Eng Fees - Percentage of Construction	5.0%
Architecture & Engineering Fees	$2,875.00
Architecture & Engineering Fees – Cost per SF	1.3 $/SF
Architecture & Engineering Fees – Cost per Unit	$40/unit

Man Hour Breakdown – Architecture Only
Average ($/Hr) Billing Rate	$75.00
		% of Construction	Each Phase	Cumulative	Cost per SF	Cost per SF Cumulative	Hours dedicated to each phase	Weeks – 1/8 person	Weeks – 1/5 person	Weeks – ¼ person	Weeks – 1/3 person	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1: / Pre-Design & Programming	10.00%	0.50%	$287.50	$287.50	$0.13	$0.13	4 hrs	0.8 wks	0.5 wks	0.4 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks	0.0 wks	0.0 wks	0.0 wks
Phase 2: / Schematic Design	25.00%	1.25%	$718.75	$1,006.25	$0.31	$0.44	10 hrs	1.9 wks	1.2 wks	1.0 wks	0.7 wks	0.5 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks
Phase 3: / Design Development	20.00%	1.00%	$575.00	$1,581.25	$0.25	$0.69	8 hrs	1.5 wks	1.0 wks	0.8 wks	0.6 wks	0.4 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks	0.1 wks
Phase 4: / Construction Documents	20.00%	1.00%	$575.00	$2,156.25	$0.25	$0.94	8 hrs	1.5 wks	1.0 wks	0.8 wks	0.6 wks	0.4 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks	0.1 wks
Phase 5: / Bidding and Issuing for Permit	5.00%	0.25%	$143.75	$2,300.00	$0.06	$1.00	2 hrs	0.4 wks	0.2 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks	0.0 wks	0.0 wks	0.0 wks	0.0 wks	0.0 wks
Phase 6: / Construction Administration	20.00%	1.00%	$575.00	$2,875.00	$0.25	$1.25	8 hrs	1.5 wks	1.0 wks	0.8 wks	0.6 wks	0.4 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks	0.1 wks
	100.00%	5.00%	$2,875.00	$2,875.00	$1.25	$1.25	38 hrs	7.7 wks	4.8 wks	3.8 wks	2.9 wks	1.9 wks	1.3 wks	1.0 wks	0.6 wks	0.5 wks	0.4 wks	0.3 wks
						1.9 months	1.2 months	1 months	.7 months	.5 months	.3 months	.2 months	.2 months	.1 months	.1 months	.1 months

## Hourly Rates - Entire Team
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	Cost with Approach (A)	Cost with Approach (B)	Cost with Approach (C)	A Rough Estimated Percentage of Overall Construction Costs	Percentage of Architectural Fees	Cost per SF	Cost per Unit
Architecture				100%	$2,875	$3,393	$3,910	5.00%	100.0%	1.3 $/SF	40 $/SF
Principal	$85/HR	$95/HR	$125/HR
Project Architect	$65/HR	$75/HR	$105/HR
Intern	$55/HR	$65/HR	$95/HR
Structural Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$160/HR	$170/HR	$180/HR
Engineer II	$135/HR	$145/HR	$155/HR
Engineer I	$125/HR	$135/HR	$145/HR
Civil Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$135/HR	$145/HR	$155/HR
Engineer II	$120/HR	$130/HR	$140/HR
Engineer I	$100/HR	$110/HR	$120/HR
Mechanical Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Electrical Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$150/HR	$160/HR	$170/HR
Engineer II	$100/HR	$110/HR	$120/HR
Engineer I	$90/HR	$100/HR	$110/HR
Plumbing Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Lighting				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Skill Level 1	$100/HR	$110/HR	$120/HR
Skill Level 2	$90/HR	$100/HR	$110/HR
Skill Level 3	$80/HR	$90/HR	$100/HR

Potential Additional Consultants				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
• Building Envelope Consultant
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				100%	$2,875	$3,393	$3,910	5.0%		1.3 $/SF	40.5 $/SF

## Hourly Rates - ARCH
Discipline	Approach / (A)	Approach / (B)	Approach / (C)
Architecture	0	0	0
Principal	$85/HR	$95/HR	$125/HR
Project Architect	$65/HR	$75/HR	$105/HR
Intern	$55/HR	$65/HR	$95/HR

## Hourly Rates - ARCH & STRUCT
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	Cost with Approach (A)	Cost with Approach (B)	Cost with Approach (C)
Architecture	0	0	0	100%	$2,875	$3,393	$3,910
Principal	$85/HR	$95/HR	$125/HR
Project Architect	$65/HR	$75/HR	$105/HR
Intern	$55/HR	$65/HR	$95/HR
Structural Engineer	0	0	0	0%	$0	$0	$0
Engineer III	$160/HR	$170/HR	$180/HR
Engineer II	$135/HR	$145/HR	$155/HR
Engineer I	$125/HR	$135/HR	$145/HR
Totals				100%	$2,875	$3,393	$3,910

## Increments
Increment Percentage	0.90%
Time Increment	1.1

## Fee Breakdown-$ & %
%	Phase	Approach (A)				Approach (B)				Approach (C)
		Rough % of Const. Costs	Estimated Duration	Not-To-Exceed		Rough % of Const. Costs	Estimated Duration	Not-To-Exceed		Rough % of Const. Costs	Estimated Duration	Not-To-Exceed
10.00%	Phase 1: / Pre-Design & Programming	0.5%	0.3 wks	$288		0.6%	0.4 wks	$339		0.7%	0.5 wks	$391
25.00%	Phase 2: / Schematic Design	1.3%	0.7 wks	$719		1.5%	1.0 wks	$848		1.7%	1.2 wks	$978
20.00%	Phase 3: / Design Development	1.0%	0.6 wks	$575		1.2%	0.8 wks	$679		1.4%	1.0 wks	$782
20.00%	Phase 4: / Construction Documents	1.0%	0.6 wks	$575		1.2%	0.8 wks	$679		1.4%	1.0 wks	$782
5.00%	Phase 5: / Bidding and Issuing for Permit	0.3%	0.1 wks	$144		0.3%	0.2 wks	$170		0.3%	0.2 wks	$196
20.00%	Phase 6: / Construction Administration	1.0%	n/a	$575		1.2%	n/a	$679		1.4%	n/a	$782
100.00%	All Phases	5.0%	2.4 wks	$2,875		5.90%	3.1 wks	$3,393		6.80%	3.9 wks	$3,910
Assuming a Construction Cost, please see note below =												$57,500

## Fee Breakdown-%
%	Phase	Approach (A)			Approach (B)			Approach (C)
		Rough % of Const. Costs	Estimated Duration		Rough % of Const. Costs	Estimated Duration		Rough % of Const. Costs	Estimated Duration
10.00%	Phase 1: / Pre-Design & Programming	0.5%	0.3 wks		0.6%	0.4 wks		0.7%	0.5 wks
25.00%	Phase 2: / Schematic Design	1.3%	0.7 wks		1.5%	1.0 wks		1.7%	1.2 wks
20.00%	Phase 3: / Design Development	1.0%	0.6 wks		1.2%	0.8 wks		1.4%	1.0 wks
20.00%	Phase 4: / Construction Documents	1.0%	0.6 wks		1.2%	0.8 wks		1.4%	1.0 wks
5.00%	Phase 5: / Bidding and Issuing for Permit	0.3%	0.1 wks		0.3%	0.2 wks		0.3%	0.2 wks
20.00%	Phase 6: / Construction Administration	1.0%	n/a		1.2%	n/a		1.4%	n/a
100.00%	All Phases	5.0%	2.4 wks		5.90%	3.1 wks		6.80%	3.9 wks

## Fee Breakdown-$
%	Phase	Approach (A)			Approach (B)			Approach (C)
		Not-To-Exceed	Estimated Duration		Not-To-Exceed	Estimated Duration		Not-To-Exceed	Estimated Duration
10.00%	Phase 1: / Pre-Design & Programming	$288	0.3 wks		$339	0.4 wks		$391	0.5 wks
25.00%	Phase 2: / Schematic Design	$719	0.7 wks		$848	1.0 wks		$978	1.2 wks
20.00%	Phase 3: / Design Development	$575	0.6 wks		$679	0.8 wks		$782	1.0 wks
20.00%	Phase 4: / Construction Documents	$575	0.6 wks		$679	0.8 wks		$782	1.0 wks
5.00%	Phase 5: / Bidding and Issuing for Permit	$144	0.1 wks		$170	0.2 wks		$196	0.2 wks
20.00%	Phase 6: / Construction Administration	$575	n/a		$679	n/a		$782	n/a
100.00%	All Phases	$2,875	2.4 wks		$3,393	3.1 wks		$3,910	3.9 wks

## Fees Per Disapline
Disciplines	Approach (A)		Approach (B)		Approach (C)
Architecture	5.00%	$2,875	5.90%	$3,393	6.80%	$3,910
Structural Engineer	0.0%	$0	0.00%	$0	0.00%	$0
Civil Engineer	0.0%	$0	0.00%	$0	0.00%	$0
Mechanical Engineer	0.0%	$0	0.00%	$0	0.00%	$0
Electrical Engineer	0.00%	$0	0.00%	$0	0.00%	$0
Plumbing Engineer	0.00%	$0	0.00%	$0	0.00%	$0
Lighting	0.00%	$0	0.00%	$0	0.00%	$0
Potential Additional Consultants	0.00%	$0	0.00%	$0	0.00%	$0
Totals	5.0%	$2,875	5.9%	$3,393	6.8%	$3,910

## Details
Start	$300
Number of Details	58
Increments	$20

	Cost Per Detail			Total
Approach A	$300	-	$320	$17,400	-	$18,560
Approach B	$340	-	$360	$19,720	-	$20,880
Approach C	$380	-	$400	$22,040	-	$23,200