## Splash
License: / This document, like most OpeningDesign's projects, is open source (Attribution-ShareAlike 4.0 International--CC BY-SA 4.0)--freely available to any party, for any use, assuming the terms such as Attribution and ShareAlike are honored.

## Fee Breakdown
		Approach (A)		Approach (B)		Approach (C)		Estimated Duration
%	Phase	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Cost Per SF
5.00%	Phase 1: / Pre-Design & Programming	0.5%	$7,088	0.6%	$7,763	0.6%	$8,438	2.0 wks	$0.79
10.00%	Phase 2: / Schematic Design	1.1%	$14,175	1.2%	$15,525	1.3%	$16,875	3.0 wks	$1.58
20.00%	Phase 3: / Design Development	2.1%	$28,350	2.3%	$31,050	2.5%	$33,750	6.0 wks	$3.15
40.00%	Phase 4: / Construction Documents	4.2%	$56,700	4.6%	$62,100	5.0%	$67,500	11.0 wks	$6.30
5.00%	Phase 5: / Bidding & Contract Negotiation	0.5%	$7,088	0.6%	$7,763	0.6%	$8,438	2.0 wks	$0.79
20.00%	Phase 6: / Construction Administration	2.1%	$28,350	2.3%	$31,050	2.5%	$33,750	n/a	$3.15
100.00%	All Phases	10.5%	$141,750	11.5%	$155,250	12.5%	$168,750	24.0 wks (Design Only)	$15.75
Assuming a Construction Cost (without equipment) =							$1,350,000

	Disciplines	Approach (A)		Approach (B)		Approach (C)
	Architecture	6.00%	$81,000	6.57%	$88,714	7.14%	$96,429		$9.00
	Structural Engineer	1.0%	$13,500	1.10%	$14,786	1.19%	$16,071		$1.50
	Civil Engineer	0.8%	$10,800	0.88%	$11,829	0.95%	$12,857		$1.20
	Mechanical Engineer	0.5%	$6,750	0.55%	$7,393	0.60%	$8,036		$0.75
	Electrical Engineer	0.50%	$6,750	0.55%	$7,393	0.60%	$8,036		$0.75
	Plumbing Engineer	0.50%	$6,750	0.55%	$7,393	0.60%	$8,036		$0.75
	Lighting	0.60%	$8,100	0.66%	$8,871	0.71%	$9,643
	Potential Additional Consultants	0.60%	$8,100	0.66%	$8,871	0.71%	$9,643		$0.90
	Totals	10.5%	$141,750	11.5%	$155,250	12.5%	$168,750		$15.75

## Hour Breakdown
Square Footage	9,000 SF
How Many Dwelling Units	56 units
Estimated Dollar per Square Footage	150 $/SF
Total Estimated Construction Costs	$1,350,000.00
Architecture Fees - Percentage of Construction	6.0%
Architecture Fees Only	$81,000.00
Architecture Fees – Cost per SF	9.0 $/SF
Architecture Fees – Cost per Unit	$1446/unit

Architecture & Eng Fees - Percentage of Construction	10.5%
Architecture & Engineering Fees	$141,750.00
Architecture & Engineering Fees – Cost per SF	15.8 $/SF
Architecture & Engineering Fees – Cost per Unit	$2531/unit

Man Hour Breakdown – Architecture Only
Average ($/Hr) Billing Rate	$75.00
		% of Construction	Each Phase	Cumulative	Cost per SF	Cost per SF Cumulative	Hours dedicated to each phase	Weeks – 1/3 person	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1 - Programming	5.00%	0.30%	$4,050.00	$4,050.00	$0.45	$0.45	54 hrs	4.2 wks	2.7 wks	1.8 wks	1.4 wks	0.9 wks	0.7 wks	0.5 wks	0.5 wks
Phase 2 - Schematic	10.00%	0.60%	$8,100.00	$12,150.00	$0.90	$1.35	108 hrs	8.3 wks	5.4 wks	3.6 wks	2.7 wks	1.8 wks	1.4 wks	1.1 wks	0.9 wks
Phase 3 - Design Development	20.00%	1.20%	$16,200.00	$28,350.00	$1.80	$3.15	216 hrs	16.6 wks	10.8 wks	7.2 wks	5.4 wks	3.6 wks	2.7 wks	2.2 wks	1.8 wks
Phase 4 - Construction Documents	40.00%	2.40%	$32,400.00	$60,750.00	$3.60	$6.75	432 hrs	33.2 wks	21.6 wks	14.4 wks	10.8 wks	7.2 wks	5.4 wks	4.3 wks	3.6 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	0.30%	$4,050.00	$64,800.00	$0.45	$7.20	54 hrs	4.2 wks	2.7 wks	1.8 wks	1.4 wks	0.9 wks	0.7 wks	0.5 wks	0.5 wks
Phase 6 - Construction Administration	20.00%	1.20%	$16,200.00	$81,000.00	$1.80	$9.00	216 hrs	16.6 wks	10.8 wks	7.2 wks	5.4 wks	3.6 wks	2.7 wks	2.2 wks	1.8 wks
	100.00%	6.00%	$81,000.00	$81,000.00	$9.00	$9.00	1,080 hrs	83.1 wks	54.0 wks	36.0 wks	27.0 wks	18.0 wks	13.5 wks	10.8 wks	9.0 wks
						20.8 months	13.5 months	9 months	6.8 months	4.5 months	3.4 months	2.7 months	2.3 months

## Hourly Rates
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Overall Construction Costs	Cost with Approach (A)		A Rough Estimated Percentage of Fees	Percentage of Architectural Fees	Cost per SF	Cost per Unit
Architecture				6.00%	$81,000		57.1%	100.0%	9.0 $/SF	1,446 $/SF
Principal	$85/HR	$95/HR	$105/HR
Project Architect	$75/HR	$85/HR	$95/HR
Intern	$55/HR	$65/HR	$75/HR
Structural Engineer				1.00%	$13,500		9.5%	16.7%	1.5 $/SF	241 $/SF
Director of Structural Engineering	$170/HR	$180/HR	$190/HR
Project Engineer	$150/HR	$160/HR	$170/HR
Design Engineer	$125/HR	$135/HR	$145/HR
Associate Engineer	$100/HR	$110/HR	$120/HR
Senior BIM Drafter	$115/HR	$125/HR	$135/HR
Junior BIM drafter	$85/HR	$95/HR	$105/HR
Civil Engineer				0.80%	$10,800		7.6%	13.3%	1.2 $/SF	193 $/SF
Engineer III	$125/HR	$135/HR	$145/HR
Engineer II	$110/HR	$120/HR	$130/HR
Engineer I	$100/HR	$110/HR	$120/HR
Mechanical Engineer				0.50%	$6,750	$20,250	4.8%	8.3%	.8 $/SF	121 $/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Electrical Engineer				0.50%	$6,750		4.8%	8.3%	.8 $/SF	121 $/SF
Engineer III	$150/HR	$160/HR	$170/HR
Engineer II	$100/HR	$110/HR	$120/HR
Engineer I	$90/HR	$100/HR	$110/HR
Plumbing Engineer				0.50%	$6,750		4.8%	8.3%	.8 $/SF	121 $/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Lighting				0.60%	$8,100		5.7%	10.0%	.9 $/SF	145 $/SF
Skill Level 1	$100/HR	$110/HR	$120/HR
Skill Level 2	$90/HR	$100/HR	$110/HR
Skill Level 3	$80/HR	$90/HR	$100/HR

Potential Additional Consultants				0.60%	$8,100		5.7%	10.0%	.9 $/SF	145 $/SF
• Building Envelope Consultant
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				10.5%	$141,750		100.0%		15.8 $/SF	2,531.3 $/SF

## Details
Start	$190
Number of Details	5
Increments	$20

	Cost Per Detail			Total
Approach A	$190	-	$210	$950	-	$1,050
Approach B	$230	-	$250	$1,150	-	$1,250
Approach C	$270	-	$290	$1,350	-	$1,450