## Splash
License: / This document, like most OpeningDesign's projects, is open source (Attribution-ShareAlike 4.0 International--CC BY-SA 4.0)--freely available to any party, for any use, assuming the terms such as Attribution and ShareAlike are honored.

## Hour Breakdown
Square Footage	1,800 SF
How Many Dwelling Units	71 units
Estimated Dollar per Square Footage	100 $/SF
Total Estimated Construction Costs	$180,000.00
Architecture Fees - Percentage of Construction	5.5%
Architecture Fees Only	$9,900.00
Architecture Fees – Cost per SF	5.5 $/SF
Architecture Fees – Cost per Unit	$139/unit

Architecture & Eng Fees - Percentage of Construction	5.5%
Architecture & Engineering Fees	$9,900.00
Architecture & Engineering Fees – Cost per SF	5.5 $/SF
Architecture & Engineering Fees – Cost per Unit	$139/unit

Man Hour Breakdown – Architecture Only
Average ($/Hr) Billing Rate	$75.00
		% of Construction	Each Phase	Cumulative	Cost per SF	Cost per SF Cumulative	Hours dedicated to each phase	Weeks – ¼ person	Weeks – 1/3 person	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1 - Programming	10.00%	0.55%	$990.00	$990.00	$0.55	$0.55	13 hrs	1.3 wks	1.0 wks	0.7 wks	0.4 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks	0.1 wks
Phase 2 - Schematic	25.00%	1.38%	$2,475.00	$3,465.00	$1.38	$1.93	33 hrs	3.3 wks	2.5 wks	1.7 wks	1.1 wks	0.8 wks	0.6 wks	0.4 wks	0.3 wks	0.3 wks
Phase 3 - Design Development	20.00%	1.10%	$1,980.00	$5,445.00	$1.10	$3.03	26 hrs	2.6 wks	2.0 wks	1.3 wks	0.9 wks	0.7 wks	0.4 wks	0.3 wks	0.3 wks	0.2 wks
Phase 4 - Construction Documents	20.00%	1.10%	$1,980.00	$7,425.00	$1.10	$4.13	26 hrs	2.6 wks	2.0 wks	1.3 wks	0.9 wks	0.7 wks	0.4 wks	0.3 wks	0.3 wks	0.2 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	0.28%	$495.00	$7,920.00	$0.28	$4.40	7 hrs	0.7 wks	0.5 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks	0.1 wks
Phase 6 - Construction Administration	20.00%	1.10%	$1,980.00	$9,900.00	$1.10	$5.50	26 hrs	2.6 wks	2.0 wks	1.3 wks	0.9 wks	0.7 wks	0.4 wks	0.3 wks	0.3 wks	0.2 wks
	100.00%	5.50%	$9,900.00	$9,900.00	$5.50	$5.50	132 hrs	13.2 wks	10.2 wks	6.6 wks	4.4 wks	3.3 wks	2.2 wks	1.7 wks	1.3 wks	1.1 wks
						3.3 months	2.5 months	1.7 months	1.1 months	.8 months	.5 months	.4 months	.3 months	.3 months

## Fee Breakdown
%	Phase	Approach (A)			Approach (B)			Approach (C)					Increment Percentage	1.00%
		Not-To-Exceed	Estimated Duration	Rough % of Const. Costs	Not-To-Exceed	Estimated Duration	Rough % of Const. Costs	Not-To-Exceed	Estimated Duration	Rough % of Const. Costs		Cost Per SF	Time Increment	1.1
20.00%	Phase 1: / Pre-Design & Programming	$1,980	1.0 wks	1.1%	$2,340	1.3 wks	1.3%	$2,700	1.7 wks	1.5%		$1.10
15.00%	Phase 2: / Schematic Design	$1,485	2.0 wks	0.8%	$1,755	2.6 wks	1.0%	$2,025	3.3 wks	1.1%		$0.83
20.00%	Phase 3: / Design Development	$1,980	2.0 wks	1.1%	$2,340	2.6 wks	1.3%	$2,700	3.3 wks	1.5%		$1.10
20.00%	Phase 4: / Construction Documents	$1,980	2.0 wks	1.1%	$2,340	2.6 wks	1.3%	$2,700	3.3 wks	1.5%		$1.10
5.00%	Phase 5: / Bidding & Contract Negotiation	$495	1.0 wks	0.3%	$585	1.3 wks	0.3%	$675	1.7 wks	0.4%		$0.28
20.00%	Phase 6: / Construction Administration	$1,980	n/a	1.1%	$2,340	n/a	1.3%	$2,700	n/a	1.5%		$1.10
100.00%	All Phases	$9,900	8.0 wks	5.5%	$11,700	10.4 wks	6.50%	$13,500	13.2 wks	7.50%		$5.50
Assuming a Construction Cost, please see note below =										$180,000

	Disciplines	Approach (A)			Approach (B)			Approach (C)
	Architecture	5.50%	$9,900		6.50%	$11,700		7.50%	$13,500
	Structural Engineer	0.0%	$0		0.00%	$0		0.00%	$0
	Civil Engineer	0.0%	$0		0.00%	$0		0.00%	$0
	Mechanical Engineer	0.0%	$0		0.00%	$0		0.00%	$0
	Electrical Engineer	0.00%	$0		0.00%	$0		0.00%	$0
	Plumbing Engineer	0.00%	$0		0.00%	$0		0.00%	$0
	Lighting	0.00%	$0		0.00%	$0		0.00%	$0
	Potential Additional Consultants	0.00%	$0		0.00%	$0		0.00%	$0
	Totals	5.5%	$9,900		6.5%	$11,700		7.5%	$13,500

## Hourly Rates
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	Cost with Approach (A)	Cost with Approach (B)	Cost with Approach (C)	A Rough Estimated Percentage of Overall Construction Costs	Percentage of Architectural Fees	Cost per SF	Cost per Unit
Architecture				100%	$9,900	$11,700	$13,500	5.50%	100.0%	5.5 $/SF	139 $/SF
Principal	$75/HR	$85/HR	$115/HR
Project Architect	$65/HR	$75/HR	$105/HR
Intern	$55/HR	$65/HR	$95/HR
Structural Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$160/HR	$170/HR	$180/HR
Engineer II	$135/HR	$145/HR	$155/HR
Engineer I	$125/HR	$135/HR	$145/HR
Civil Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$135/HR	$145/HR	$155/HR
Engineer II	$120/HR	$130/HR	$140/HR
Engineer I	$100/HR	$110/HR	$120/HR
Mechanical Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Electrical Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$150/HR	$160/HR	$170/HR
Engineer II	$100/HR	$110/HR	$120/HR
Engineer I	$90/HR	$100/HR	$110/HR
Plumbing Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Lighting				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Skill Level 1	$100/HR	$110/HR	$120/HR
Skill Level 2	$90/HR	$100/HR	$110/HR
Skill Level 3	$80/HR	$90/HR	$100/HR

Potential Additional Consultants				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
• Building Envelope Consultant
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				100%	$9,900	$11,700	$13,500	5.5%		5.5 $/SF	139.4 $/SF

## Details
Start	$300
Number of Details	58
Increments	$20

	Cost Per Detail			Total
Approach A	$300	-	$320	$17,400	-	$18,560
Approach B	$340	-	$360	$19,720	-	$20,880
Approach C	$380	-	$400	$22,040	-	$23,200