## Fee Breakdown
		Approach (A)		Approach (B)		Approach (C)
%	Phase	% Const. Costs	Not-To-Exceed	% Const. Costs	Not-To-Exceed	% Const. Costs	Not-To-Exceed

5.0%	Phase 1: / Programming	0.4%	$375	0.4%	$425	0.5%	$475
10.0%	Phase 2: / Schematic Design	0.8%	$750	0.9%	$850	1.0%	$950
25.0%	Phase 3: / Design Development	1.9%	$1,875	2.1%	$2,125	2.4%	$2,375
35.0%	Phase 4: / Construction Documents	2.6%	$2,625	3.0%	$2,975	3.3%	$3,325
5.0%	Phase 5: / Bidding & Contract Negotiation	0.4%	$375	0.4%	$425	0.5%	$475
20.0%	Phase 6: / Construction Administration	1.5%	$1,500	1.7%	$1,700	1.9%	$1,900

100.0%	All Phases	7.5%	$7,500	8.5%	$8,500	9.5%	$9,500
Assuming a Construction Cost =							$100,000

## Hour Breakdown
Square Footage - Existing	7,000 SF
Dollar per Square Footage	115 $/SF
Total Estimated Construction Costs	$805,000.00
Architecture Fees - Percentage of Construction	7.5%
Architecture/Engineering Fees	$60,375.00

Average ($/Hr) Billing Rate	$75.00
		Each Phase	Cumulative	Hours dedicated to each phase	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people
Phase 1 - Programming	5.00%	$2,012.50	$2,012.50	27 hrs	1.3 wks	0.9 wks	0.7 wks	0.4 wks	0.3 wks
Phase 2 - Schematic	10.00%	$4,025.00	$6,037.50	54 hrs	2.7 wks	1.8 wks	1.3 wks	0.9 wks	0.7 wks
Phase 3 - Design Development	25.00%	$10,062.50	$16,100.00	134 hrs	6.7 wks	4.5 wks	3.4 wks	2.2 wks	1.7 wks
Phase 4 - Construction Documents	35.00%	$14,087.50	$30,187.50	188 hrs	9.4 wks	6.3 wks	4.7 wks	3.1 wks	2.3 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$2,012.50	$32,200.00	27 hrs	1.3 wks	0.9 wks	0.7 wks	0.4 wks	0.3 wks
Phase 6 - Construction Administration	20.00%	$8,050.00	$40,250.00	107 hrs	5.4 wks	3.6 wks	2.7 wks	1.8 wks	1.3 wks
	100.00%	$40,250.00	$40,250.00	537 hrs	26.8 wks	17.9 wks	13.4 wks	8.9 wks	6.7 wks

Architecture	5.0%	67%	$40,250.00
Structural	1.3%	17%	$10,062.50
Civil	1.3%	17%	$10,062.50
	7.50%	100.00%