## Splash
License: / This document, like most OpeningDesign's projects, is open source (Attribution-ShareAlike 4.0 International--CC BY-SA 4.0)--freely available to any party, for any use, assuming the terms such as Attribution and ShareAlike are honored.

## Hour Breakdown
Square Footage	2,100 SF
How Many Dwelling Units	71 units
Estimated Dollar per Square Footage	100 $/SF
Total Estimated Construction Costs	$210,000.00
Architecture Fees - Percentage of Construction	4.5%
Architecture Fees Only	$9,450.00
Architecture Fees – Cost per SF	4.5 $/SF
Architecture Fees – Cost per Unit	$133/unit

Architecture & Eng Fees - Percentage of Construction	4.5%
Architecture & Engineering Fees	$9,450.00
Architecture & Engineering Fees – Cost per SF	4.5 $/SF
Architecture & Engineering Fees – Cost per Unit	$133/unit

Man Hour Breakdown – Architecture Only
Average ($/Hr) Billing Rate	$75.00
		% of Construction	Each Phase	Cumulative	Cost per SF	Cost per SF Cumulative	Hours dedicated to each phase	Weeks – 1/8 person	Weeks – 1/5 person	Weeks – ¼ person	Weeks – 1/3 person	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1: / Pre-Design & Programming	10.00%	0.45%	$945.00	$945.00	$0.45	$0.45	13 hrs	2.5 wks	1.6 wks	1.3 wks	1.0 wks	0.6 wks	0.4 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks	0.1 wks
Phase 2: / Schematic Design	25.00%	1.13%	$2,362.50	$3,307.50	$1.13	$1.58	32 hrs	6.3 wks	3.9 wks	3.2 wks	2.4 wks	1.6 wks	1.1 wks	0.8 wks	0.5 wks	0.4 wks	0.3 wks	0.3 wks
Phase 3: / Design Development	20.00%	0.90%	$1,890.00	$5,197.50	$0.90	$2.48	25 hrs	5.0 wks	3.2 wks	2.5 wks	1.9 wks	1.3 wks	0.8 wks	0.6 wks	0.4 wks	0.3 wks	0.3 wks	0.2 wks
Phase 4: / Construction Documents	20.00%	0.90%	$1,890.00	$7,087.50	$0.90	$3.38	25 hrs	5.0 wks	3.2 wks	2.5 wks	1.9 wks	1.3 wks	0.8 wks	0.6 wks	0.4 wks	0.3 wks	0.3 wks	0.2 wks
Phase 5: / Bidding & Contract Negotiation	5.00%	0.23%	$472.50	$7,560.00	$0.23	$3.60	6 hrs	1.3 wks	0.8 wks	0.6 wks	0.5 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks	0.1 wks
Phase 6: / Construction Administration	20.00%	0.90%	$1,890.00	$9,450.00	$0.90	$4.50	25 hrs	5.0 wks	3.2 wks	2.5 wks	1.9 wks	1.3 wks	0.8 wks	0.6 wks	0.4 wks	0.3 wks	0.3 wks	0.2 wks
	100.00%	4.50%	$9,450.00	$9,450.00	$4.50	$4.50	126 hrs	25.2 wks	15.8 wks	12.6 wks	9.7 wks	6.3 wks	4.2 wks	3.2 wks	2.1 wks	1.6 wks	1.3 wks	1.1 wks
						6.3 months	3.9 months	3.2 months	2.4 months	1.6 months	1.1 months	.8 months	.5 months	.4 months	.3 months	.3 months

## Hourly Rates - Entire Team
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	Cost with Approach (A)	Cost with Approach (B)	Cost with Approach (C)	A Rough Estimated Percentage of Overall Construction Costs	Percentage of Architectural Fees	Cost per SF	Cost per Unit
Architecture				100%	$9,450	$11,550	$13,650	4.50%	100.0%	4.5 $/SF	133 $/SF
Principal	$85/HR	$95/HR	$125/HR
Project Architect	$65/HR	$75/HR	$105/HR
Intern	$55/HR	$65/HR	$95/HR
Structural Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$160/HR	$170/HR	$180/HR
Engineer II	$135/HR	$145/HR	$155/HR
Engineer I	$125/HR	$135/HR	$145/HR
Civil Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$135/HR	$145/HR	$155/HR
Engineer II	$120/HR	$130/HR	$140/HR
Engineer I	$100/HR	$110/HR	$120/HR
Mechanical Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Electrical Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$150/HR	$160/HR	$170/HR
Engineer II	$100/HR	$110/HR	$120/HR
Engineer I	$90/HR	$100/HR	$110/HR
Plumbing Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Lighting				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Skill Level 1	$100/HR	$110/HR	$120/HR
Skill Level 2	$90/HR	$100/HR	$110/HR
Skill Level 3	$80/HR	$90/HR	$100/HR

Potential Additional Consultants				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
• Building Envelope Consultant
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				100%	$9,450	$11,550	$13,650	4.5%		4.5 $/SF	133.1 $/SF

## Hourly Rates - ARCH
Discipline	Approach / (A)	Approach / (B)	Approach / (C)
Architecture	0	0	0
Principal	$85/HR	$95/HR	$125/HR
Project Architect	$65/HR	$75/HR	$105/HR
Intern	$55/HR	$65/HR	$95/HR

## Hourly Rates - ARCH & STRUCT
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	Cost with Approach (A)	Cost with Approach (B)	Cost with Approach (C)
Architecture	0	0	0	100%	$9,450	$11,550	$13,650
Principal	$85/HR	$95/HR	$125/HR
Project Architect	$65/HR	$75/HR	$105/HR
Intern	$55/HR	$65/HR	$95/HR
Structural Engineer	0	0	0	0%	$0	$0	$0
Engineer III	$160/HR	$170/HR	$180/HR
Engineer II	$135/HR	$145/HR	$155/HR
Engineer I	$125/HR	$135/HR	$145/HR
Totals				100%	$9,450	$11,550	$13,650

## Increments
Increment Percentage	1.00%
Time Increment	1.1

## Fee Breakdown-$ & %
%	Phase	Approach (A)				Approach (B)				Approach (C)
		Rough % of Const. Costs	Estimated Duration	Not-To-Exceed		Rough % of Const. Costs	Estimated Duration	Not-To-Exceed		Rough % of Const. Costs	Estimated Duration	Not-To-Exceed
10.00%	Phase 1: / Pre-Design & Programming	0.5%	1.0 wks	$945		0.6%	1.3 wks	$1,155		0.7%	1.7 wks	$1,365
25.00%	Phase 2: / Schematic Design	1.1%	2.4 wks	$2,363		1.4%	3.3 wks	$2,888		1.6%	4.2 wks	$3,413
20.00%	Phase 3: / Design Development	0.9%	1.9 wks	$1,890		1.1%	2.6 wks	$2,310		1.3%	3.4 wks	$2,730
20.00%	Phase 4: / Construction Documents	0.9%	1.9 wks	$1,890		1.1%	2.6 wks	$2,310		1.3%	3.4 wks	$2,730
5.00%	Phase 5: / Bidding & Contract Negotiation	0.2%	0.5 wks	$473		0.3%	0.7 wks	$578		0.3%	0.8 wks	$683
20.00%	Phase 6: / Construction Administration	0.9%	n/a	$1,890		1.1%	n/a	$2,310		1.3%	n/a	$2,730
100.00%	All Phases	4.5%	7.8 wks	$9,450		5.50%	10.4 wks	$11,550		6.50%	13.6 wks	$13,650
Assuming a Construction Cost, please see note below =												$210,000

## Fee Breakdown-%
%	Phase	Approach (A)			Approach (B)			Approach (C)
		Rough % of Const. Costs	Estimated Duration		Rough % of Const. Costs	Estimated Duration		Rough % of Const. Costs	Estimated Duration
10.00%	Phase 1: / Pre-Design & Programming	0.5%	1.0 wks		0.6%	1.3 wks		0.7%	1.7 wks
25.00%	Phase 2: / Schematic Design	1.1%	2.4 wks		1.4%	3.3 wks		1.6%	4.2 wks
20.00%	Phase 3: / Design Development	0.9%	1.9 wks		1.1%	2.6 wks		1.3%	3.4 wks
20.00%	Phase 4: / Construction Documents	0.9%	1.9 wks		1.1%	2.6 wks		1.3%	3.4 wks
5.00%	Phase 5: / Bidding & Contract Negotiation	0.2%	0.5 wks		0.3%	0.7 wks		0.3%	0.8 wks
20.00%	Phase 6: / Construction Administration	0.9%	n/a		1.1%	n/a		1.3%	n/a
100.00%	All Phases	4.5%	7.8 wks		5.50%	10.4 wks		6.50%	13.6 wks

## Fee Breakdown-$
%	Phase	Approach (A)			Approach (B)			Approach (C)
		Not-To-Exceed	Estimated Duration		Not-To-Exceed	Estimated Duration		Not-To-Exceed	Estimated Duration
10.00%	Phase 1: / Pre-Design & Programming	$945	1.0 wks		$1,155	1.3 wks		$1,365	1.7 wks
25.00%	Phase 2: / Schematic Design	$2,363	2.4 wks		$2,888	3.3 wks		$3,413	4.2 wks
20.00%	Phase 3: / Design Development	$1,890	1.9 wks		$2,310	2.6 wks		$2,730	3.4 wks
20.00%	Phase 4: / Construction Documents	$1,890	1.9 wks		$2,310	2.6 wks		$2,730	3.4 wks
5.00%	Phase 5: / Bidding & Contract Negotiation	$473	0.5 wks		$578	0.7 wks		$683	0.8 wks
20.00%	Phase 6: / Construction Administration	$1,890	n/a		$2,310	n/a		$2,730	n/a
100.00%	All Phases	$9,450	7.8 wks		$11,550	10.4 wks		$13,650	13.6 wks

## Fees Per Disapline
Disciplines	Approach (A)		Approach (B)		Approach (C)
Architecture	4.50%	$9,450	5.50%	$11,550	6.50%	$13,650
Structural Engineer	0.0%	$0	0.00%	$0	0.00%	$0
Civil Engineer	0.0%	$0	0.00%	$0	0.00%	$0
Mechanical Engineer	0.0%	$0	0.00%	$0	0.00%	$0
Electrical Engineer	0.00%	$0	0.00%	$0	0.00%	$0
Plumbing Engineer	0.00%	$0	0.00%	$0	0.00%	$0
Lighting	0.00%	$0	0.00%	$0	0.00%	$0
Potential Additional Consultants	0.00%	$0	0.00%	$0	0.00%	$0
Totals	4.5%	$9,450	5.5%	$11,550	6.5%	$13,650

## Details
Start	$300
Number of Details	58
Increments	$20

	Cost Per Detail			Total
Approach A	$300	-	$320	$17,400	-	$18,560
Approach B	$340	-	$360	$19,720	-	$20,880
Approach C	$380	-	$400	$22,040	-	$23,200