## Fee Breakdown
		Approach (A)		Approach (B)		Approach (C)		Estimated Duration
%	Phase	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs
10.00%	Phase 1: / Programming	0.7%	$1,350	0.8%	$1,550	0.9%	$1,750	2.0 wks
20.00%	Phase 2: / Schematic Design	1.4%	$2,700	1.6%	$3,100	1.8%	$3,500	3.0 wks
15.00%	Phase 3: / Design Development	1.0%	$2,025	1.2%	$2,325	1.3%	$2,625	2.0 wks
30.00%	Phase 4: / Construction Documents	2.0%	$4,050	2.3%	$4,650	2.6%	$5,250	4.0 wks
5.00%	Phase 5: / Bidding & Contract Negotiation	0.3%	$675	0.4%	$775	0.4%	$875	1.0 wks
20.00%	Phase 6: / Construction Administration	1.4%	$2,700	1.6%	$3,100	1.8%	$3,500	n/a
100.00%	All Phases	6.8%	$13,500	7.8%	$15,500	8.8%	$17,500
Assuming a Construction Cost =							$200,000

## Hour Breakdown
Square Footage	23,000 SF
Estimated Dollar per Square Footage	50 $/SF
Total Estimated Construction Costs	$200,000.00
Architecture/Eng Fees - Percentage of Construction	6.8%
Architecture & Engineering Fees	$13,500.00

Average ($/Hr) Billing Rate	$55.00
		Each Phase	Cumulative	Hours dedicated to each phase	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1 - Programming	10.00%	$1,350.00	$1,350.00	25 hrs	1.2 wks	0.8 wks	0.6 wks	0.4 wks	0.3 wks	0.2 wks	0.2 wks
Phase 2 - Schematic	20.00%	$2,700.00	$4,050.00	49 hrs	2.5 wks	1.6 wks	1.2 wks	0.8 wks	0.6 wks	0.5 wks	0.4 wks
Phase 3 - Design Development	15.00%	$2,025.00	$6,075.00	37 hrs	1.8 wks	1.2 wks	0.9 wks	0.6 wks	0.5 wks	0.4 wks	0.3 wks
Phase 4 - Construction Documents	30.00%	$4,050.00	$10,125.00	74 hrs	3.7 wks	2.5 wks	1.8 wks	1.2 wks	0.9 wks	0.7 wks	0.6 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$675.00	$10,800.00	12 hrs	0.6 wks	0.4 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks	0.1 wks
Phase 6 - Construction Administration	20.00%	$2,700.00	$13,500.00	49 hrs	2.5 wks	1.6 wks	1.2 wks	0.8 wks	0.6 wks	0.5 wks	0.4 wks
	100.00%	$13,500.00	$13,500.00	245 hrs	12.3 wks	8.2 wks	6.1 wks	4.1 wks	3.1 wks	2.5 wks	2.0 wks

## Hourly Rates
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	A Rough Estimated Percentage of Overall Construction Costs
Architecture (OpeningDesign)				88.9%	6.0%
Skill Level 1	$75/HR	$85/HR	$95/HR
Skill Level 2	$65/HR	$75/HR	$85/HR
Level 3	$45/HR	$55/HR	$65/HR
Civil Engineer (Quam Engineering)				0.0%	0.0%
Level 1	$125/HR	$135/HR	$145/HR
Level 2	$110/HR	$120/HR	$130/HR
Level 3	$100/HR	$110/HR	$120/HR
Structural Engineer				7.4%	0.5%
Skill Level 1	$75/HR	$85/HR	$95/HR
Level 2	$100/HR	$110/HR	$120/HR
Level 3	$90/HR	$100/HR	$110/HR
Mechanical Engineer (Desapex)				0.0%	0.0%
Level 1	$45/HR	$55/HR	$65/HR
Level 2	$35/HR	$45/HR	$55/HR
Level 3	$35/HR	$45/HR	$55/HR
Electrical Engineer (OpeningDesign)				0.0%	0.0%
Level 1	$150/HR	$160/HR	$170/HR
Level 2	$100/HR	$110/HR	$120/HR
Level 3	$90/HR	$100/HR	$110/HR
Plumbing Engineer (Zenteno Solutions)				0.0%	0.0%
Level 1	$70/HR	$80/HR	$90/HR
Level 2	$60/HR	$70/HR	$80/HR
Level 3	$50/HR	$60/HR	$70/HR
LEED Consulting (OpeningDesign)				0.0%	0.0%
Level 1	$85/HR	$95/HR	$105/HR
Level 2	$70/HR	$80/HR	$90/HR
Level 3	$60/HR	$70/HR	$80/HR
Potential Additional Consultants				3.7%	0.3%
• Lighting
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				100.0%	6.8%