## Splash
License: / This document, like most OpeningDesign's projects, is open source (Attribution-ShareAlike 4.0 International--CC BY-SA 4.0)--freely available to any party, for any use, assuming the terms such as Attribution and ShareAlike are honored.

## Fee Breakdown
		Approach (A)		Approach (B)		Approach (C)		Estimated Duration
%	Phase	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Cost Per SF
15.00%	Phase 1: / Pre-Design & Programming	1.1%	$945	1.3%	$1,071	1.4%	$1,197	2.0 wks	$0.79
15.00%	Phase 2: / Schematic Design	1.1%	$945	1.3%	$1,071	1.4%	$1,197	2.0 wks	$0.79
15.00%	Phase 3: / Design Development	1.1%	$945	1.3%	$1,071	1.4%	$1,197	2.0 wks	$0.79
30.00%	Phase 4: / Construction Documents	2.3%	$1,890	2.6%	$2,142	2.9%	$2,394	3.0 wks	$1.58
5.00%	Phase 5: / Bidding & Contract Negotiation	0.4%	$315	0.4%	$357	0.5%	$399	1.0 wks	$0.26
20.00%	Phase 6: / Construction Administration	1.5%	$1,260	1.7%	$1,428	1.9%	$1,596	n/a	$1.05
100.00%	All Phases	7.5%	$6,300	8.5%	$7,140	9.5%	$7,980	10.0 wks (Design Only)	$5.25
Assuming a Construction Cost (without equipment) =							$84,000

	Disciplines	Approach (A)		Approach (B)		Approach (C)
	Architecture	6.50%	$5,460	7.37%	$6,188	8.23%	$6,916		$4.55
	Structural Engineer	1.0%	$840	1.13%	$952	1.27%	$1,064		$0.70
	Civil Engineer	0.0%	$0	0.00%	$0	0.00%	$0		$0.00
	Mechanical Engineer	0.0%	$0	0.00%	$0	0.00%	$0		$0.00
	Electrical Engineer	0.00%	$0	0.00%	$0	0.00%	$0		$0.00
	Plumbing Engineer	0.00%	$0	0.00%	$0	0.00%	$0		$0.00
	Lighting	0.00%	$0	0.00%	$0	0.00%	$0
	Potential Additional Consultants	0.00%	$0	0.00%	$0	0.00%	$0		$0.00
	Totals	7.5%	$6,300	8.5%	$7,140	9.5%	$7,980		$5.25

## Hour Breakdown
Square Footage	1,200 SF
How Many Dwelling Units	56 units
Estimated Dollar per Square Footage	70 $/SF
Total Estimated Construction Costs	$84,000.00
Architecture Fees - Percentage of Construction	6.5%
Architecture Fees Only	$5,460.00
Architecture Fees – Cost per SF	4.6 $/SF
Architecture Fees – Cost per Unit	$98/unit

Architecture & Eng Fees - Percentage of Construction	7.5%
Architecture & Engineering Fees	$6,300.00
Architecture & Engineering Fees – Cost per SF	5.3 $/SF
Architecture & Engineering Fees – Cost per Unit	$113/unit

Man Hour Breakdown – Architecture Only
Average ($/Hr) Billing Rate	$75.00
		% of Construction	Each Phase	Cumulative	Cost per SF	Cost per SF Cumulative	Hours dedicated to each phase	Weeks – ¼ person	Weeks – 1/3 person	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1 - Programming	15.00%	0.98%	$819.00	$819.00	$0.68	$0.68	11 hrs	1.1 wks	0.8 wks	0.5 wks	0.4 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks
Phase 2 - Schematic	15.00%	0.98%	$819.00	$1,638.00	$0.68	$1.37	11 hrs	1.1 wks	0.8 wks	0.5 wks	0.4 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks
Phase 3 - Design Development	15.00%	0.98%	$819.00	$2,457.00	$0.68	$2.05	11 hrs	1.1 wks	0.8 wks	0.5 wks	0.4 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks
Phase 4 - Construction Documents	30.00%	1.95%	$1,638.00	$4,095.00	$1.37	$3.41	22 hrs	2.2 wks	1.7 wks	1.1 wks	0.7 wks	0.5 wks	0.4 wks	0.3 wks	0.2 wks	0.2 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	0.33%	$273.00	$4,368.00	$0.23	$3.64	4 hrs	0.4 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks	0.0 wks	0.0 wks	0.0 wks
Phase 6 - Construction Administration	20.00%	1.30%	$1,092.00	$5,460.00	$0.91	$4.55	15 hrs	1.5 wks	1.1 wks	0.7 wks	0.5 wks	0.4 wks	0.2 wks	0.2 wks	0.1 wks	0.1 wks
	100.00%	6.50%	$5,460.00	$5,460.00	$4.55	$4.55	73 hrs	7.3 wks	5.6 wks	3.6 wks	2.4 wks	1.8 wks	1.2 wks	0.9 wks	0.7 wks	0.6 wks
						1.8 months	1.4 months	.9 months	.6 months	.5 months	.3 months	.2 months	.2 months	.2 months

## Hourly Rates
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Overall Construction Costs	Cost with Approach (A)		A Rough Estimated Percentage of Fees	Percentage of Architectural Fees	Cost per SF	Cost per Unit
Architecture				6.50%	$5,460		86.7%	100.0%	4.6 $/SF	98 $/SF
Principal	$85/HR	$95/HR	$105/HR
Project Architect	$75/HR	$85/HR	$95/HR
Intern	$55/HR	$65/HR	$75/HR
Structural Engineer				1.00%	$840		13.3%	15.4%	.7 $/SF	15 $/SF
Director of Structural Engineering	$170/HR	$180/HR	$190/HR
Project Engineer	$150/HR	$160/HR	$170/HR
Design Engineer	$125/HR	$135/HR	$145/HR
Associate Engineer	$100/HR	$110/HR	$120/HR
Senior BIM Drafter	$115/HR	$125/HR	$135/HR
Junior BIM drafter	$85/HR	$95/HR	$105/HR
Civil Engineer				0.00%	$0		0.0%	0.0%	.0 $/SF	$/SF
Engineer III	$125/HR	$135/HR	$145/HR
Engineer II	$110/HR	$120/HR	$130/HR
Engineer I	$100/HR	$110/HR	$120/HR
Mechanical Engineer				0.00%	$0	$0	0.0%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Electrical Engineer				0.00%	$0		0.0%	0.0%	.0 $/SF	$/SF
Engineer III	$150/HR	$160/HR	$170/HR
Engineer II	$100/HR	$110/HR	$120/HR
Engineer I	$90/HR	$100/HR	$110/HR
Plumbing Engineer				0.00%	$0		0.0%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Lighting				0.00%	$0		0.0%	0.0%	.0 $/SF	$/SF
Skill Level 1	$100/HR	$110/HR	$120/HR
Skill Level 2	$90/HR	$100/HR	$110/HR
Skill Level 3	$80/HR	$90/HR	$100/HR

Potential Additional Consultants				0.00%	$0		0.0%	0.0%	.0 $/SF	$/SF
• Building Envelope Consultant
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				7.5%	$6,300		100.0%		5.3 $/SF	112.5 $/SF

## Details
Start	$190
Number of Details	5
Increments	$20

	Cost Per Detail			Total
Approach A	$190	-	$210	$950	-	$1,050
Approach B	$230	-	$250	$1,150	-	$1,250
Approach C	$270	-	$290	$1,350	-	$1,450