## Splash
License: / This document, like most OpeningDesign's projects, is open source (Attribution-ShareAlike 4.0 International--CC BY-SA 4.0)--freely available to any party, for any use, assuming the terms such as Attribution and ShareAlike are honored.

## Fee Breakdown
%	Phase	Approach (A)	Estimated Duration	Approach (B)		Approach (C)		Approach A	Approach B	Approach C		Increment Percentage	1.00%
		Rough % of Const. Costs	Estimated Duration	Rough % of Const. Costs	Estimated Duration	Rough % of Const. Costs	Estimated Duration	Not-To-Exceed	Not-To-Exceed	Not-To-Exceed	Cost Per SF	Time Increment	1.1
20.00%	Phase 1: / Pre-Design & Programming	1.7%	1.0 wks	1.9%	1.2 wks	2.1%	1.5 wks	$1,660	$1,860	$2,060	$1.66
15.00%	Phase 2: / Schematic Design	1.2%	1.0 wks	1.4%	1.2 wks	1.5%	1.5 wks	$1,245	$1,395	$1,545	$1.25
20.00%	Phase 3: / Design Development	1.7%	1.0 wks	1.9%	1.2 wks	2.1%	1.5 wks	$1,660	$1,860	$2,060	$1.66
20.00%	Phase 4: / Construction Documents	1.7%	2.0 wks	1.9%	2.5 wks	2.1%	3.0 wks	$1,660	$1,860	$2,060	$1.66
5.00%	Phase 5: / Bidding & Contract Negotiation	0.4%	1.0 wks	0.5%	1.2 wks	0.5%	1.5 wks	$415	$465	$515	$0.42
20.00%	Phase 6: / Construction Administration	1.7%	n/a	1.9%	n/a	2.1%	n/a	$1,660	$1,860	$2,060	$1.66
100.00%	All Phases	8.3%	6.0 wks	9.30%	7.4 wks	10.30%	9.0 wks	$8,300	$9,300	$10,300	$8.30
								Assuming a Construction Cost, please see note below =			$100,000
	Disciplines	Approach (A)		Approach (B)		Approach (C)
	Architecture	6.30%		7.06%		7.82%		$6,300	$7,059	$7,818	$6.30
	Structural Engineer	1.0%		1.12%		1.24%		$1,000	$1,120	$1,241	$1.00
	Civil Engineer	1.0%		1.12%		1.24%		$1,000	$1,120	$1,241	$1.00
	Mechanical Engineer	0.0%		0.00%		0.00%		$0	$0	$0	$0.00
	Electrical Engineer	0.00%		0.00%		0.00%		$0	$0	$0	$0.00
	Plumbing Engineer	0.00%		0.00%		0.00%		$0	$0	$0	$0.00
	Lighting	0.00%		0.00%		0.00%		$0	$0	$0	$0.00
	Potential Additional Consultants	0.00%		0.00%		0.00%		$0	$0	$0	$0.00
	Totals	8.3%		9.3%		10.3%		$8,300	$9,300	$10,300	$8.30

## Hour Breakdown
Square Footage	1,000 SF
How Many Dwelling Units	71 units
Estimated Dollar per Square Footage	100 $/SF
Total Estimated Construction Costs	$100,000.00
Architecture Fees - Percentage of Construction	6.3%
Architecture Fees Only	$6,300.00
Architecture Fees – Cost per SF	6.3 $/SF
Architecture Fees – Cost per Unit	$89/unit

Architecture & Eng Fees - Percentage of Construction	8.3%
Architecture & Engineering Fees	$8,300.00
Architecture & Engineering Fees – Cost per SF	8.3 $/SF
Architecture & Engineering Fees – Cost per Unit	$117/unit

Man Hour Breakdown – Architecture Only
Average ($/Hr) Billing Rate	$75.00
		% of Construction	Each Phase	Cumulative	Cost per SF	Cost per SF Cumulative	Hours dedicated to each phase	Weeks – ¼ person	Weeks – 1/3 person	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1 - Programming	20.00%	1.26%	$1,260.00	$1,260.00	$1.26	$1.26	17 hrs	1.7 wks	1.3 wks	0.8 wks	0.6 wks	0.4 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks
Phase 2 - Schematic	15.00%	0.95%	$945.00	$2,205.00	$0.95	$2.21	13 hrs	1.3 wks	1.0 wks	0.6 wks	0.4 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks	0.1 wks
Phase 3 - Design Development	20.00%	1.26%	$1,260.00	$3,465.00	$1.26	$3.47	17 hrs	1.7 wks	1.3 wks	0.8 wks	0.6 wks	0.4 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks
Phase 4 - Construction Documents	45.00%	2.84%	$2,835.00	$6,300.00	$2.84	$6.30	38 hrs	3.8 wks	2.9 wks	1.9 wks	1.3 wks	0.9 wks	0.6 wks	0.5 wks	0.4 wks	0.3 wks
Phase 5 - Bidding and Construction Contract Negotiation	7.00%	0.44%	$441.00	$6,741.00	$0.44	$6.74	6 hrs	0.6 wks	0.5 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks	0.1 wks	0.0 wks
Phase 6 - Construction Administration	30.00%	1.89%	$1,890.00	$8,631.00	$1.89	$8.63	25 hrs	2.5 wks	1.9 wks	1.3 wks	0.8 wks	0.6 wks	0.4 wks	0.3 wks	0.3 wks	0.2 wks
	137.00%	8.63%	$8,631.00	$8,631.00	$8.63	$8.63	115 hrs	11.5 wks	8.9 wks	5.8 wks	3.8 wks	2.9 wks	1.9 wks	1.4 wks	1.2 wks	1.0 wks
						2.9 months	2.2 months	1.4 months	1 months	.7 months	.5 months	.4 months	.3 months	.2 months

## Hourly Rates
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	Cost with Approach (A)	Cost with Approach (B)	Cost with Approach (C)	A Rough Estimated Percentage of Overall Construction Costs	Percentage of Architectural Fees	Cost per SF	Cost per Unit
Architecture				76%	$6,300	$7,059	$7,818	6.30%	100.0%	6.3 $/SF	89 $/SF
Principal	$85/HR	$95/HR	$125/HR
Project Architect	$75/HR	$85/HR	$115/HR
Intern	$65/HR	$75/HR	$105/HR
Structural Engineer				12%	$1,000	$1,120	$1,241	1.00%	15.9%	1.0 $/SF	14 $/SF
Engineer III	$160/HR	$170/HR	$180/HR
Engineer II	$135/HR	$145/HR	$155/HR
Engineer I	$125/HR	$135/HR	$145/HR
Civil Engineer				12%	$1,000	$1,120	$1,241	1.00%	15.9%	1.0 $/SF	14 $/SF
Engineer III	$135/HR	$145/HR	$155/HR
Engineer II	$120/HR	$130/HR	$140/HR
Engineer I	$100/HR	$110/HR	$120/HR
Mechanical Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Electrical Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$150/HR	$160/HR	$170/HR
Engineer II	$100/HR	$110/HR	$120/HR
Engineer I	$90/HR	$100/HR	$110/HR
Plumbing Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Lighting				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Skill Level 1	$100/HR	$110/HR	$120/HR
Skill Level 2	$90/HR	$100/HR	$110/HR
Skill Level 3	$80/HR	$90/HR	$100/HR

Potential Additional Consultants				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
• Building Envelope Consultant
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				100%	$8,300	$9,300	$10,300	8.3%		8.3 $/SF	116.9 $/SF

## Details
Start	$300
Number of Details	58
Increments	$20

	Cost Per Detail			Total
Approach A	$300	-	$320	$17,400	-	$18,560
Approach B	$340	-	$360	$19,720	-	$20,880
Approach C	$380	-	$400	$22,040	-	$23,200