## Splash
License: / This document, like most OpeningDesign's projects, is open source (Attribution-ShareAlike 4.0 International--CC BY-SA 4.0)--freely available to any party, for any use, assuming the terms such as Attribution and ShareAlike are honored.

## Hour Breakdown
Square Footage	3,200 SF
How Many Dwelling Units	71 units
Estimated Dollar per Square Footage	100 $/SF
Total Estimated Construction Costs	$320,000.00
Architecture Fees - Percentage of Construction	4.7%
Architecture Fees Only	$15,040.00
Architecture Fees – Cost per SF	4.7 $/SF
Architecture Fees – Cost per Unit	$212/unit

Architecture & Eng Fees - Percentage of Construction	5.2%
Architecture & Engineering Fees	$16,640.00
Architecture & Engineering Fees – Cost per SF	5.2 $/SF
Architecture & Engineering Fees – Cost per Unit	$234/unit

Man Hour Breakdown – Architecture Only
Average ($/Hr) Billing Rate	$75.00
		% of Construction	Each Phase	Cumulative	Cost per SF	Cost per SF Cumulative	Hours dedicated to each phase	Weeks – 1/8 person	Weeks – 1/5 person	Weeks – ¼ person	Weeks – 1/3 person	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1: / Pre-Design & Programming	10.00%	0.47%	$1,504.00	$1,504.00	$0.47	$0.47	20 hrs	4.0 wks	2.5 wks	2.0 wks	1.5 wks	1.0 wks	0.7 wks	0.5 wks	0.3 wks	0.3 wks	0.2 wks	0.2 wks
Phase 2: / Schematic Design	25.00%	1.18%	$3,760.00	$5,264.00	$1.18	$1.65	50 hrs	10.0 wks	6.3 wks	5.0 wks	3.9 wks	2.5 wks	1.7 wks	1.3 wks	0.8 wks	0.6 wks	0.5 wks	0.4 wks
Phase 3: / Design Development	20.00%	0.94%	$3,008.00	$8,272.00	$0.94	$2.59	40 hrs	8.0 wks	5.0 wks	4.0 wks	3.1 wks	2.0 wks	1.3 wks	1.0 wks	0.7 wks	0.5 wks	0.4 wks	0.3 wks
Phase 4: / Construction Documents	20.00%	0.94%	$3,008.00	$11,280.00	$0.94	$3.53	40 hrs	8.0 wks	5.0 wks	4.0 wks	3.1 wks	2.0 wks	1.3 wks	1.0 wks	0.7 wks	0.5 wks	0.4 wks	0.3 wks
Phase 5: / Bidding & Contract Negotiation	5.00%	0.24%	$752.00	$12,032.00	$0.24	$3.76	10 hrs	2.0 wks	1.3 wks	1.0 wks	0.8 wks	0.5 wks	0.3 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks
Phase 6: / Construction Administration	20.00%	0.94%	$3,008.00	$15,040.00	$0.94	$4.70	40 hrs	8.0 wks	5.0 wks	4.0 wks	3.1 wks	2.0 wks	1.3 wks	1.0 wks	0.7 wks	0.5 wks	0.4 wks	0.3 wks
	100.00%	4.70%	$15,040.00	$15,040.00	$4.70	$4.70	201 hrs	40.1 wks	25.1 wks	20.1 wks	15.4 wks	10.0 wks	6.7 wks	5.0 wks	3.3 wks	2.5 wks	2.0 wks	1.7 wks
						10 months	6.3 months	5 months	3.9 months	2.5 months	1.7 months	1.3 months	.8 months	.6 months	.5 months	.4 months

## Hourly Rates - Entire Team
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	Cost with Approach (A)	Cost with Approach (B)	Cost with Approach (C)	A Rough Estimated Percentage of Overall Construction Costs	Percentage of Architectural Fees	Cost per SF	Cost per Unit
Architecture				90%	$15,040	$17,932	$20,825	4.70%	100.0%	4.7 $/SF	212 $/SF
Principal	$85/HR	$95/HR	$125/HR
Project Architect	$65/HR	$75/HR	$105/HR
Intern	$55/HR	$65/HR	$95/HR
Structural Engineer				10%	$1,600	$1,908	$2,215	0.50%	10.6%	.5 $/SF	23 $/SF
Engineer III	$160/HR	$170/HR	$180/HR
Engineer II	$135/HR	$145/HR	$155/HR
Engineer I	$125/HR	$135/HR	$145/HR
Civil Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$135/HR	$145/HR	$155/HR
Engineer II	$120/HR	$130/HR	$140/HR
Engineer I	$100/HR	$110/HR	$120/HR
Mechanical Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Electrical Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$150/HR	$160/HR	$170/HR
Engineer II	$100/HR	$110/HR	$120/HR
Engineer I	$90/HR	$100/HR	$110/HR
Plumbing Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Lighting				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Skill Level 1	$100/HR	$110/HR	$120/HR
Skill Level 2	$90/HR	$100/HR	$110/HR
Skill Level 3	$80/HR	$90/HR	$100/HR

Potential Additional Consultants				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
• Building Envelope Consultant
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				100%	$16,640	$19,840	$23,040	5.2%		5.2 $/SF	234.4 $/SF

## Hourly Rates - ARCH
Discipline	Approach / (A)	Approach / (B)	Approach / (C)
Architecture	0	0	0
Principal	$85/HR	$95/HR	$125/HR
Project Architect	$65/HR	$75/HR	$105/HR
Intern	$55/HR	$65/HR	$95/HR

## Hourly Rates - ARCH & STRUCT
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	Cost with Approach (A)	Cost with Approach (B)	Cost with Approach (C)
Architecture	0	0	0	90%	$15,040	$17,932	$20,825
Principal	$85/HR	$95/HR	$125/HR
Project Architect	$65/HR	$75/HR	$105/HR
Intern	$55/HR	$65/HR	$95/HR
Structural Engineer	0	0	0	10%	$1,600	$1,908	$2,215
Engineer III	$160/HR	$170/HR	$180/HR
Engineer II	$135/HR	$145/HR	$155/HR
Engineer I	$125/HR	$135/HR	$145/HR
Totals				100%	$16,640	$19,840	$23,040

## Increments
Increment Percentage	1.00%
Time Increment	1.1

## Fee Breakdown-$ & %
%	Phase	Approach (A)				Approach (B)				Approach (C)
		Rough % of Const. Costs	Estimated Duration	Not-To-Exceed		Rough % of Const. Costs	Estimated Duration	Not-To-Exceed		Rough % of Const. Costs	Estimated Duration	Not-To-Exceed
10.00%	Phase 1: / Pre-Design & Programming	0.5%	1.5 wks	$1,664		0.6%	2.0 wks	$1,984		0.7%	2.6 wks	$2,304
25.00%	Phase 2: / Schematic Design	1.3%	3.9 wks	$4,160		1.6%	5.1 wks	$4,960		1.8%	6.5 wks	$5,760
20.00%	Phase 3: / Design Development	1.0%	3.1 wks	$3,328		1.2%	4.0 wks	$3,968		1.4%	5.2 wks	$4,608
20.00%	Phase 4: / Construction Documents	1.0%	3.1 wks	$3,328		1.2%	4.0 wks	$3,968		1.4%	5.2 wks	$4,608
5.00%	Phase 5: / Bidding & Contract Negotiation	0.3%	0.8 wks	$832		0.3%	1.0 wks	$992		0.4%	1.3 wks	$1,152
20.00%	Phase 6: / Construction Administration	1.0%	n/a	$3,328		1.2%	n/a	$3,968		1.4%	n/a	$4,608
100.00%	All Phases	5.2%	12.3 wks	$16,640		6.20%	16.2 wks	$19,840		7.20%	20.7 wks	$23,040
Assuming a Construction Cost, please see note below =												$320,000

## Fee Breakdown-%
%	Phase	Approach (A)			Approach (B)			Approach (C)
		Rough % of Const. Costs	Estimated Duration		Rough % of Const. Costs	Estimated Duration		Rough % of Const. Costs	Estimated Duration
10.00%	Phase 1: / Pre-Design & Programming	0.5%	1.5 wks		0.6%	2.0 wks		0.7%	2.6 wks
25.00%	Phase 2: / Schematic Design	1.3%	3.9 wks		1.6%	5.1 wks		1.8%	6.5 wks
20.00%	Phase 3: / Design Development	1.0%	3.1 wks		1.2%	4.0 wks		1.4%	5.2 wks
20.00%	Phase 4: / Construction Documents	1.0%	3.1 wks		1.2%	4.0 wks		1.4%	5.2 wks
5.00%	Phase 5: / Bidding & Contract Negotiation	0.3%	0.8 wks		0.3%	1.0 wks		0.4%	1.3 wks
20.00%	Phase 6: / Construction Administration	1.0%	n/a		1.2%	n/a		1.4%	n/a
100.00%	All Phases	5.2%	12.3 wks		6.20%	16.2 wks		7.20%	20.7 wks

## Fee Breakdown-$
%	Phase	Approach (A)			Approach (B)			Approach (C)
		Not-To-Exceed	Estimated Duration		Not-To-Exceed	Estimated Duration		Not-To-Exceed	Estimated Duration
10.00%	Phase 1: / Pre-Design & Programming	$1,664	1.5 wks		$1,984	2.0 wks		$2,304	2.6 wks
25.00%	Phase 2: / Schematic Design	$4,160	3.9 wks		$4,960	5.1 wks		$5,760	6.5 wks
20.00%	Phase 3: / Design Development	$3,328	3.1 wks		$3,968	4.0 wks		$4,608	5.2 wks
20.00%	Phase 4: / Construction Documents	$3,328	3.1 wks		$3,968	4.0 wks		$4,608	5.2 wks
5.00%	Phase 5: / Bidding & Contract Negotiation	$832	0.8 wks		$992	1.0 wks		$1,152	1.3 wks
20.00%	Phase 6: / Construction Administration	$3,328	n/a		$3,968	n/a		$4,608	n/a
100.00%	All Phases	$16,640	12.3 wks		$19,840	16.2 wks		$23,040	20.7 wks

## Fees Per Disapline
Disciplines	Approach (A)		Approach (B)		Approach (C)
Architecture	4.70%	$15,040	5.60%	$17,932	6.51%	$20,825
Structural Engineer	0.5%	$1,600	0.60%	$1,908	0.69%	$2,215
Civil Engineer	0.0%	$0	0.00%	$0	0.00%	$0
Mechanical Engineer	0.0%	$0	0.00%	$0	0.00%	$0
Electrical Engineer	0.00%	$0	0.00%	$0	0.00%	$0
Plumbing Engineer	0.00%	$0	0.00%	$0	0.00%	$0
Lighting	0.00%	$0	0.00%	$0	0.00%	$0
Potential Additional Consultants	0.00%	$0	0.00%	$0	0.00%	$0
Totals	5.2%	$16,640	6.2%	$19,840	7.2%	$23,040

## Details
Start	$300
Number of Details	58
Increments	$20

	Cost Per Detail			Total
Approach A	$300	-	$320	$17,400	-	$18,560
Approach B	$340	-	$360	$19,720	-	$20,880
Approach C	$380	-	$400	$22,040	-	$23,200