## Fee Breakdown
		Approach (A)		Approach (B)		Approach (C)		Estimated Duration
%	Phase	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs
10.00%	Phase 1: / Pre-Design & Programming	0.6%	$840	0.7%	$980	0.8%	$1,120	2.0 wks
20.00%	Phase 2: / Schematic Design	1.2%	$1,680	1.4%	$1,960	1.6%	$2,240	3.0 wks
15.00%	Phase 3: / Design Development	0.9%	$1,260	1.1%	$1,470	1.2%	$1,680	2.0 wks
30.00%	Phase 4: / Construction Documents	1.8%	$2,520	2.1%	$2,940	2.4%	$3,360	4.0 wks
5.00%	Phase 5: / Bidding & Contract Negotiation	0.3%	$420	0.4%	$490	0.4%	$560	1.0 wks
20.00%	Phase 6: / Construction Administration	1.2%	$1,680	1.4%	$1,960	1.6%	$2,240	n/a
100.00%	All Phases	6.0%	$8,400	7.0%	$9,800	8.0%	$11,200
Assuming a Construction Cost =							$140,000

## Hour Breakdown
Square Footage	1,400 SF
Estimated Dollar per Square Footage	100 $/SF
Total Estimated Construction Costs	$140,000.00
Architecture/Eng Fees - Percentage of Construction	6.0%
Architecture & Engineering Fees	$8,400.00

Average ($/Hr) Billing Rate	$55.00
		Each Phase	Cumulative	Hours dedicated to each phase	Weeks – 1/3 person	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1 - Programming	10.00%	$840.00	$840.00	15 hrs	1.2 wks	0.8 wks	0.5 wks	0.4 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks
Phase 2 - Schematic	20.00%	$1,680.00	$2,520.00	31 hrs	2.3 wks	1.5 wks	1.0 wks	0.8 wks	0.5 wks	0.4 wks	0.3 wks	0.3 wks
Phase 3 - Design Development	15.00%	$1,260.00	$3,780.00	23 hrs	1.8 wks	1.1 wks	0.8 wks	0.6 wks	0.4 wks	0.3 wks	0.2 wks	0.2 wks
Phase 4 - Construction Documents	30.00%	$2,520.00	$6,300.00	46 hrs	3.5 wks	2.3 wks	1.5 wks	1.1 wks	0.8 wks	0.6 wks	0.5 wks	0.4 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$420.00	$6,720.00	8 hrs	0.6 wks	0.4 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks	0.1 wks
Phase 6 - Construction Administration	20.00%	$1,680.00	$8,400.00	31 hrs	2.3 wks	1.5 wks	1.0 wks	0.8 wks	0.5 wks	0.4 wks	0.3 wks	0.3 wks
	100.00%	$8,400.00	$8,400.00	153 hrs	11.7 wks	7.6 wks	5.1 wks	3.8 wks	2.5 wks	1.9 wks	1.5 wks	1.3 wks

## Hourly Rates
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	A Rough Estimated Percentage of Overall Construction Costs
Architecture (OpeningDesign)				83.3%	5.0%	$7,000.00
Skill Level 1	$75/HR	$85/HR	$95/HR
Skill Level 2	$65/HR	$75/HR	$85/HR
Skill Level 3	$45/HR	$55/HR	$65/HR
Civil Engineer (Quam Engineering)				0.0%	0.0%	$0.00
Skill Level 1	$125/HR	$135/HR	$145/HR
Skill Level 2	$110/HR	$120/HR	$130/HR
Skill Level 3	$100/HR	$110/HR	$120/HR
Structural Engineer				16.7%	1.0%	$1,400.00
Skill Level 1	$150/HR	$160/HR	$170/HR
Skill Level 2	$120/HR	$130/HR	$140/HR
Skill Level 3	$100/HR	$110/HR	$120/HR
Mechanical Engineer (Desapex)				0.0%	0.0%	$0.00
Skill Level 1	$45/HR	$55/HR	$65/HR
Skill Level 2	$35/HR	$45/HR	$55/HR
Skill Level 3	$35/HR	$45/HR	$55/HR
Electrical Engineer (OpeningDesign)				0.0%	0.0%	$0.00
Skill Level 1	$150/HR	$160/HR	$170/HR
Skill Level 2	$100/HR	$110/HR	$120/HR
Skill Level 3	$90/HR	$100/HR	$110/HR
Plumbing Engineer (Zenteno Solutions)				0.0%	0.0%	$0.00
Skill Level 1	$70/HR	$80/HR	$90/HR
Skill Level 2	$60/HR	$70/HR	$80/HR
Skill Level 3	$50/HR	$60/HR	$70/HR
LEED Consulting (OpeningDesign)				0.0%	0.0%	$0.00
Skill Level 1	$85/HR	$95/HR	$105/HR
Skill Level 2	$70/HR	$80/HR	$90/HR
Skill Level 3	$60/HR	$70/HR	$80/HR
Potential Additional Consultants				0.0%	0.0%	$0.00
• Lighting
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				100.0%	6.0%	$8,400.00