## Splash
License: / This document, like most OpeningDesign's projects, is open source (Attribution-ShareAlike 4.0 International--CC BY-SA 4.0)--freely available to any party, for any use, assuming the terms such as Attribution and ShareAlike are honored.

## Hour Breakdown
Square Footage	400 SF
How Many Dwelling Units	71 units
Estimated Dollar per Square Footage	170 $/SF
Total Estimated Construction Costs	$40,000.00
Architecture Fees - Percentage of Construction	6.0%
Architecture Fees Only	$2,400.00
Architecture Fees – Cost per SF	6.0 $/SF
Architecture Fees – Cost per Unit	$34/unit

Architecture & Eng Fees - Percentage of Construction	6.0%
Architecture & Engineering Fees	$2,400.00
Architecture & Engineering Fees – Cost per SF	6.0 $/SF
Architecture & Engineering Fees – Cost per Unit	$34/unit

Man Hour Breakdown – Architecture Only
Average ($/Hr) Billing Rate	$75.00
		% of Construction	Each Phase	Cumulative	Cost per SF	Cost per SF Cumulative	Hours dedicated to each phase	Weeks – 1/10 person	Weeks – 1/8 person	Weeks – 1/5 person	Weeks – ¼ person	Weeks – 1/3 person	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1: / Pre-Design & Programming	10.00%	0.60%	$240.00	$240.00	$0.60	$0.60	3 hrs	0.8 wks	0.6 wks	0.4 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks	0.0 wks	0.0 wks	0.0 wks
Phase 2: / Schematic Design	25.00%	1.50%	$600.00	$840.00	$1.50	$2.10	8 hrs	2.0 wks	1.6 wks	1.0 wks	0.8 wks	0.6 wks	0.4 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks	0.1 wks
Phase 3: / Design Development	20.00%	1.20%	$480.00	$1,320.00	$1.20	$3.30	6 hrs	1.6 wks	1.3 wks	0.8 wks	0.6 wks	0.5 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks	0.1 wks
Phase 4: / Construction Documents	20.00%	1.20%	$480.00	$1,800.00	$1.20	$4.50	6 hrs	1.6 wks	1.3 wks	0.8 wks	0.6 wks	0.5 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks	0.1 wks
Phase 5: / Bidding and Issuing for Permit	5.00%	0.30%	$120.00	$1,920.00	$0.30	$4.80	2 hrs	0.4 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks	0.0 wks	0.0 wks	0.0 wks	0.0 wks	0.0 wks
Phase 6: / Construction Administration	20.00%	1.20%	$480.00	$2,400.00	$1.20	$6.00	6 hrs	1.6 wks	1.3 wks	0.8 wks	0.6 wks	0.5 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks	0.1 wks
	100.00%	6.00%	$2,400.00	$2,400.00	$6.00	$6.00	32 hrs	8 hrs	6.4 wks	4.0 wks	3.2 wks	2.5 wks	1.6 wks	1.1 wks	0.8 wks	0.5 wks	0.4 wks	0.3 wks	0.3 wks
						2 months	1.6 months	1 months	.8 months	.6 months	.4 months	.3 months	.2 months	.1 months	.1 months	.1 months	.1 months

## Hourly Rates - Entire Team
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	Cost with Approach (A)	Cost with Approach (B)	Cost with Approach (C)	A Rough Estimated Percentage of Overall Construction Costs	Percentage of Architectural Fees	Cost per SF	Cost per Unit
Architecture				100%	$2,400	$2,760	$3,120	6.00%	100.0%	6.0 $/SF	34 $/SF
Principal	$85/HR	$95/HR	$125/HR
Project Architect	$65/HR	$75/HR	$105/HR
Intern	$55/HR	$65/HR	$95/HR
Structural Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$160/HR	$170/HR	$180/HR
Engineer II	$135/HR	$145/HR	$155/HR
Engineer I	$125/HR	$135/HR	$145/HR
Civil Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$135/HR	$145/HR	$155/HR
Engineer II	$120/HR	$130/HR	$140/HR
Engineer I	$100/HR	$110/HR	$120/HR
Mechanical Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Electrical Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$150/HR	$160/HR	$170/HR
Engineer II	$100/HR	$110/HR	$120/HR
Engineer I	$90/HR	$100/HR	$110/HR
Plumbing Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Lighting				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Skill Level 1	$100/HR	$110/HR	$120/HR
Skill Level 2	$90/HR	$100/HR	$110/HR
Skill Level 3	$80/HR	$90/HR	$100/HR

Potential Additional Consultants				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
• Building Envelope Consultant
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				100%	$2,400	$2,760	$3,120	6.0%		6.0 $/SF	33.8 $/SF

## Hourly Rates - ARCH
Discipline	Approach / (A)	Approach / (B)	Approach / (C)
Architecture	0	0	0
Principal	$85/HR	$95/HR	$125/HR
Project Architect	$65/HR	$75/HR	$105/HR
Intern	$55/HR	$65/HR	$95/HR

## Hourly Rates - ARCH & STRUCT
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	Cost with Approach (A)	Cost with Approach (B)	Cost with Approach (C)
Architecture	0	0	0	100%	$2,400	$2,760	$3,120
Principal	$85/HR	$95/HR	$125/HR
Project Architect	$65/HR	$75/HR	$105/HR
Intern	$55/HR	$65/HR	$95/HR
Structural Engineer	0	0	0	0%	$0	$0	$0
Engineer III	$160/HR	$170/HR	$180/HR
Engineer II	$135/HR	$145/HR	$155/HR
Engineer I	$125/HR	$135/HR	$145/HR
Totals				100%	$2,400	$2,760	$3,120

## Increments
Increment Percentage	0.90%
Time Increment	1.1

## Fee Breakdown-$ & %
%	Phase	Approach (A)				Approach (B)				Approach (C)
		Rough % of Const. Costs	Estimated Duration	Not-To-Exceed		Rough % of Const. Costs	Estimated Duration	Not-To-Exceed		Rough % of Const. Costs	Estimated Duration	Not-To-Exceed
10.00%	Phase 1: / Pre-Design & Programming	0.6%	0.6 wks	$240		0.7%	0.8 wks	$276		0.8%	1.0 wks	$312
25.00%	Phase 2: / Schematic Design	1.5%	1.6 wks	$600		1.7%	2.0 wks	$690		2.0%	2.5 wks	$780
20.00%	Phase 3: / Design Development	1.2%	1.3 wks	$480		1.4%	1.6 wks	$552		1.6%	2.0 wks	$624
20.00%	Phase 4: / Construction Documents	1.2%	1.3 wks	$480		1.4%	1.6 wks	$552		1.6%	2.0 wks	$624
5.00%	Phase 5: / Bidding and Issuing for Permit	0.3%	0.3 wks	$120		0.3%	0.4 wks	$138		0.4%	0.5 wks	$156
20.00%	Phase 6: / Construction Administration	1.2%	n/a	$480		1.4%	n/a	$552		1.6%	n/a	$624
100.00%	All Phases	6.0%	5.1 wks	$2,400		6.90%	6.5 wks	$2,760		7.80%	8.1 wks	$3,120
Assuming a Construction Cost, please see note below =												$40,000

## Fee Breakdown-%
%	Phase	Approach (A)			Approach (B)			Approach (C)
		Rough % of Const. Costs	Estimated Duration		Rough % of Const. Costs	Estimated Duration		Rough % of Const. Costs	Estimated Duration
10.00%	Phase 1: / Pre-Design & Programming	0.6%	0.6 wks		0.7%	0.8 wks		0.8%	1.0 wks
25.00%	Phase 2: / Schematic Design	1.5%	1.6 wks		1.7%	2.0 wks		2.0%	2.5 wks
20.00%	Phase 3: / Design Development	1.2%	1.3 wks		1.4%	1.6 wks		1.6%	2.0 wks
20.00%	Phase 4: / Construction Documents	1.2%	1.3 wks		1.4%	1.6 wks		1.6%	2.0 wks
5.00%	Phase 5: / Bidding and Issuing for Permit	0.3%	0.3 wks		0.3%	0.4 wks		0.4%	0.5 wks
20.00%	Phase 6: / Construction Administration	1.2%	n/a		1.4%	n/a		1.6%	n/a
100.00%	All Phases	6.0%	5.1 wks		6.90%	6.5 wks		7.80%	8.1 wks

## Fee Breakdown-$
%	Phase	Approach (A)			Approach (B)			Approach (C)
		Not-To-Exceed	Estimated Duration		Not-To-Exceed	Estimated Duration		Not-To-Exceed	Estimated Duration
10.00%	Phase 1: / Pre-Design & Programming	$240	0.6 wks		$276	0.8 wks		$312	1.0 wks
25.00%	Phase 2: / Schematic Design	$600	1.6 wks		$690	2.0 wks		$780	2.5 wks
20.00%	Phase 3: / Design Development	$480	1.3 wks		$552	1.6 wks		$624	2.0 wks
20.00%	Phase 4: / Construction Documents	$480	1.3 wks		$552	1.6 wks		$624	2.0 wks
5.00%	Phase 5: / Bidding and Issuing for Permit	$120	0.3 wks		$138	0.4 wks		$156	0.5 wks
20.00%	Phase 6: / Construction Administration	$480	n/a		$552	n/a		$624	n/a
100.00%	All Phases	$2,400	5.1 wks		$2,760	6.5 wks		$3,120	8.1 wks

## Fees Per Disapline
Disciplines	Approach (A)		Approach (B)		Approach (C)
Architecture	6.00%	$2,400	6.90%	$2,760	7.80%	$3,120
Structural Engineer	0.0%	$0	0.00%	$0	0.00%	$0
Civil Engineer	0.0%	$0	0.00%	$0	0.00%	$0
Mechanical Engineer	0.0%	$0	0.00%	$0	0.00%	$0
Electrical Engineer	0.00%	$0	0.00%	$0	0.00%	$0
Plumbing Engineer	0.00%	$0	0.00%	$0	0.00%	$0
Lighting	0.00%	$0	0.00%	$0	0.00%	$0
Potential Additional Consultants	0.00%	$0	0.00%	$0	0.00%	$0
Totals	6.0%	$2,400	6.9%	$2,760	7.8%	$3,120

## Details
Start	$300
Number of Details	58
Increments	$20

	Cost Per Detail			Total
Approach A	$300	-	$320	$17,400	-	$18,560
Approach B	$340	-	$360	$19,720	-	$20,880
Approach C	$380	-	$400	$22,040	-	$23,200