## Fee Breakdown
%	Phase	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed
10.00%	Phase 1: / Programming	0.6%	$1,440	0.7%	$1,680	0.8%	$1,920
20.00%	Phase 2: / Schematic Design	1.2%	$2,880	1.4%	$3,360	1.6%	$3,840
20.00%	Phase 3: / Design Development	1.2%	$2,880	1.4%	$3,360	1.6%	$3,840
30.00%	Phase 4: / Construction Documents	1.8%	$4,320	2.1%	$5,040	2.4%	$5,760
5.00%	Phase 5: / Bidding & Contract Negotiation	0.3%	$720	0.4%	$840	0.4%	$960
15.00%	Phase 6: / Construction Administration	0.9%	$2,160	1.1%	$2,520	1.2%	$2,880
100.00%	All Phases	6.0%	$14,400	7.0%	$16,800	8.0%	$19,200
Assuming a Construction Cost =			$240,000

## Hour Breakdown
Square Footage	2,000 SF
Estimated Dollar per Square Footage	120 $/SF
Total Estimated Construction Costs	$240,000.00
Architecture/Eng Fees - Percentage of Construction	6.0%
Architecture & Engineering Fees	$14,400.00

Average ($/Hr) Billing Rate	$55.00
		Each Phase	Cumulative	Hours dedicated to each phase	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1 - Programming	10.00%	$1,440.00	$1,440.00	26 hrs	1.3 wks	0.9 wks	0.7 wks	0.4 wks	0.3 wks	0.3 wks	0.2 wks
Phase 2 - Schematic	20.00%	$2,880.00	$4,320.00	52 hrs	2.6 wks	1.7 wks	1.3 wks	0.9 wks	0.7 wks	0.5 wks	0.4 wks
Phase 3 - Design Development	20.00%	$2,880.00	$7,200.00	52 hrs	2.6 wks	1.7 wks	1.3 wks	0.9 wks	0.7 wks	0.5 wks	0.4 wks
Phase 4 - Construction Documents	30.00%	$4,320.00	$11,520.00	79 hrs	3.9 wks	2.6 wks	2.0 wks	1.3 wks	1.0 wks	0.8 wks	0.7 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$720.00	$12,240.00	13 hrs	0.7 wks	0.4 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks	0.1 wks
Phase 6 - Construction Administration	15.00%	$2,160.00	$14,400.00	39 hrs	2.0 wks	1.3 wks	1.0 wks	0.7 wks	0.5 wks	0.4 wks	0.3 wks
	100.00%	$14,400.00	$14,400.00	262 hrs	13.1 wks	8.7 wks	6.5 wks	4.4 wks	3.3 wks	2.6 wks	2.2 wks

## Hourly Rates
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	A Rough Estimated Percentage of Overall Construction Costs
Architecture (OpeningDesign)				100.0%	6.0%
Skill Level 1	$75/HR	$85/HR	$95/HR
Skill Level 2	$65/HR	$75/HR	$85/HR
Level 3	$45/HR	$55/HR	$65/HR
Civil Engineer (Quam Engineering)				0.0%	0.0%
Level 1	$125/HR	$135/HR	$145/HR
Level 2	$110/HR	$120/HR	$130/HR
Level 3	$100/HR	$110/HR	$120/HR
Structural Engineer				0.0%	0.0%
Skill Level 1	$75/HR	$85/HR	$95/HR
Level 2	$100/HR	$110/HR	$120/HR
Level 3	$90/HR	$100/HR	$110/HR
Mechanical Engineer (Desapex)				0.0%	0.0%
Level 1	$45/HR	$55/HR	$65/HR
Level 2	$35/HR	$45/HR	$55/HR
Level 3	$35/HR	$45/HR	$55/HR
Electrical Engineer (OpeningDesign)				0.0%	0.0%
Level 1	$150/HR	$160/HR	$170/HR
Level 2	$100/HR	$110/HR	$120/HR
Level 3	$90/HR	$100/HR	$110/HR
Plumbing Engineer (Zenteno Solutions)				0.0%	0.0%
Level 1	$70/HR	$80/HR	$90/HR
Level 2	$60/HR	$70/HR	$80/HR
Level 3	$50/HR	$60/HR	$70/HR
LEED Consulting (OpeningDesign)				0.0%	0.0%
Level 1	$85/HR	$95/HR	$105/HR
Level 2	$70/HR	$80/HR	$90/HR
Level 3	$60/HR	$70/HR	$80/HR
Potential Additional Consultants				0.0%	0.0%
• Lighting
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				100.0%	6.0%