## Fee Breakdown
		Approach (A)		Approach (B)		Approach (C)		Estimated Duration
%	Phase	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs
10.00%	Phase 1: / Pre-Design & Programming	0.8%	$1,125	0.9%	$1,275	1.0%	$1,425	2.0 wks
20.00%	Phase 2: / Schematic Design	1.5%	$2,250	1.7%	$2,550	1.9%	$2,850	4.0 wks
15.00%	Phase 3: / Design Development	1.1%	$1,688	1.3%	$1,913	1.4%	$2,138	3.0 wks
30.00%	Phase 4: / Construction Documents	2.3%	$3,375	2.6%	$3,825	2.9%	$4,275	5.0 wks
5.00%	Phase 5: / Bidding & Contract Negotiation	0.4%	$563	0.4%	$638	0.5%	$713	1.0 wks
20.00%	Phase 6: / Construction Administration	1.5%	$2,250	1.7%	$2,550	1.9%	$2,850	n/a
100.00%	All Phases	7.5%	$11,250	8.5%	$12,750	9.5%	$14,250
Assuming a Construction Cost =							$150,000

## Hour Breakdown
Square Footage	2,000 SF
Estimated Dollar per Square Footage	50 $/SF
Total Estimated Construction Costs	$150,000.00
Architecture/Eng Fees - Percentage of Construction	7.5%
Architecture & Engineering Fees	$11,250.00

Average ($/Hr) Billing Rate	$55.00
		Each Phase	Cumulative	Hours dedicated to each phase	Weeks – 1/3 person	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1 - Programming	10.00%	$1,125.00	$1,125.00	20 hrs	1.6 wks	1.0 wks	0.7 wks	0.5 wks	0.3 wks	0.3 wks	0.2 wks	0.2 wks
Phase 2 - Schematic	20.00%	$2,250.00	$3,375.00	41 hrs	3.1 wks	2.0 wks	1.4 wks	1.0 wks	0.7 wks	0.5 wks	0.4 wks	0.3 wks
Phase 3 - Design Development	15.00%	$1,687.50	$5,062.50	31 hrs	2.4 wks	1.5 wks	1.0 wks	0.8 wks	0.5 wks	0.4 wks	0.3 wks	0.3 wks
Phase 4 - Construction Documents	30.00%	$3,375.00	$8,437.50	61 hrs	4.7 wks	3.1 wks	2.0 wks	1.5 wks	1.0 wks	0.8 wks	0.6 wks	0.5 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$562.50	$9,000.00	10 hrs	0.8 wks	0.5 wks	0.3 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks
Phase 6 - Construction Administration	20.00%	$2,250.00	$11,250.00	41 hrs	3.1 wks	2.0 wks	1.4 wks	1.0 wks	0.7 wks	0.5 wks	0.4 wks	0.3 wks
	100.00%	$11,250.00	$11,250.00	205 hrs	15.7 wks	10.2 wks	6.8 wks	5.1 wks	3.4 wks	2.6 wks	2.0 wks	1.7 wks

## Hourly Rates
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	A Rough Estimated Percentage of Overall Construction Costs
Architecture (OpeningDesign)				80.0%	6.0%	$9,000.00
Skill Level 1	$75/HR	$85/HR	$95/HR
Skill Level 2	$65/HR	$75/HR	$85/HR
Skill Level 3	$45/HR	$55/HR	$65/HR
Civil Engineer (Quam Engineering)				0.0%	0.0%	$0.00
Skill Level 1	$125/HR	$135/HR	$145/HR
Skill Level 2	$110/HR	$120/HR	$130/HR
Skill Level 3	$100/HR	$110/HR	$120/HR
Structural Engineer				13.3%	1.0%	$1,500.00
Skill Level 1	$150/HR	$160/HR	$170/HR
Skill Level 2	$120/HR	$130/HR	$140/HR
Skill Level 3	$100/HR	$110/HR	$120/HR
Mechanical Engineer (Desapex)				0.0%	0.0%	$0.00
Skill Level 1	$45/HR	$55/HR	$65/HR
Skill Level 2	$35/HR	$45/HR	$55/HR
Skill Level 3	$35/HR	$45/HR	$55/HR
Electrical Engineer (OpeningDesign)				0.0%	0.0%	$0.00
Skill Level 1	$150/HR	$160/HR	$170/HR
Skill Level 2	$100/HR	$110/HR	$120/HR
Skill Level 3	$90/HR	$100/HR	$110/HR
Plumbing Engineer (Zenteno Solutions)				0.0%	0.0%	$0.00
Skill Level 1	$70/HR	$80/HR	$90/HR
Skill Level 2	$60/HR	$70/HR	$80/HR
Skill Level 3	$50/HR	$60/HR	$70/HR
LEED Consulting (OpeningDesign)				0.0%	0.0%	$0.00
Skill Level 1	$85/HR	$95/HR	$105/HR
Skill Level 2	$70/HR	$80/HR	$90/HR
Skill Level 3	$60/HR	$70/HR	$80/HR
Potential Additional Consultants				6.7%	0.5%	$750.00
• Lighting
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				100.0%	7.5%	$11,250.00