## Splash
License: / This document, like most OpeningDesign's projects, is open source (Attribution-ShareAlike 4.0 International--CC BY-SA 4.0)--freely available to any party, for any use, assuming the terms such as Attribution and ShareAlike are honored.

## Fee Breakdown
%	Phase	Approach (A)	Estimated Duration	Approach (B)		Approach (C)		Approach A	Approach B	Approach C		Increment Percentage	1.00%
		Rough % of Const. Costs	Estimated Duration	Rough % of Const. Costs	Estimated Duration	Rough % of Const. Costs	Estimated Duration	Not-To-Exceed	Not-To-Exceed	Not-To-Exceed	Cost Per SF	Time Increment	1.1
20.00%	Phase 1: / Pre-Design & Programming	1.1%	2.0 wks	1.3%	2.6 wks	1.5%	3.3 wks	$2,200	$2,600	$3,000	$1.10
15.00%	Phase 2: / Schematic Design	0.8%	2.0 wks	1.0%	2.6 wks	1.1%	3.3 wks	$1,650	$1,950	$2,250	$0.83
20.00%	Phase 3: / Design Development	1.1%	2.0 wks	1.3%	2.6 wks	1.5%	3.3 wks	$2,200	$2,600	$3,000	$1.10
20.00%	Phase 4: / Construction Documents	1.1%	4.0 wks	1.3%	5.2 wks	1.5%	6.6 wks	$2,200	$2,600	$3,000	$1.10
5.00%	Phase 5: / Bidding & Contract Negotiation	0.3%	1.0 wks	0.3%	1.3 wks	0.4%	1.7 wks	$550	$650	$750	$0.28
20.00%	Phase 6: / Construction Administration	1.1%	n/a	1.3%	n/a	1.5%	n/a	$2,200	$2,600	$3,000	$1.10
100.00%	All Phases	5.5%	11.0 wks	6.50%	14.3 wks	7.50%	18.2 wks	$11,000	$13,000	$15,000	$5.50
								Assuming a Construction Cost, please see note below =			$200,000
	Disciplines	Approach (A)		Approach (B)		Approach (C)
	Architecture	5.50%		6.50%		7.50%		$11,000	$13,000	$15,000	$5.50
	Structural Engineer	0.0%		0.00%		0.00%		$0	$0	$0	$0.00
	Civil Engineer	0.0%		0.00%		0.00%		$0	$0	$0	$0.00
	Mechanical Engineer	0.0%		0.00%		0.00%		$0	$0	$0	$0.00
	Electrical Engineer	0.00%		0.00%		0.00%		$0	$0	$0	$0.00
	Plumbing Engineer	0.00%		0.00%		0.00%		$0	$0	$0	$0.00
	Lighting	0.00%		0.00%		0.00%		$0	$0	$0	$0.00
	Potential Additional Consultants	0.00%		0.00%		0.00%		$0	$0	$0	$0.00
	Totals	5.5%		6.5%		7.5%		$11,000	$13,000	$15,000	$5.50

## Hour Breakdown
Square Footage	2,000 SF
How Many Dwelling Units	71 units
Estimated Dollar per Square Footage	100 $/SF
Total Estimated Construction Costs	$200,000.00
Architecture Fees - Percentage of Construction	5.5%
Architecture Fees Only	$11,000.00
Architecture Fees – Cost per SF	5.5 $/SF
Architecture Fees – Cost per Unit	$155/unit

Architecture & Eng Fees - Percentage of Construction	5.5%
Architecture & Engineering Fees	$11,000.00
Architecture & Engineering Fees – Cost per SF	5.5 $/SF
Architecture & Engineering Fees – Cost per Unit	$155/unit

Man Hour Breakdown – Architecture Only
Average ($/Hr) Billing Rate	$75.00
		% of Construction	Each Phase	Cumulative	Cost per SF	Cost per SF Cumulative	Hours dedicated to each phase	Weeks – ¼ person	Weeks – 1/3 person	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people	Weeks – 2.5 people	Weeks – 3 people
Phase 1 - Programming	20.00%	1.10%	$2,200.00	$2,200.00	$1.10	$1.10	29 hrs	2.9 wks	2.3 wks	1.5 wks	1.0 wks	0.7 wks	0.5 wks	0.4 wks	0.3 wks	0.2 wks
Phase 2 - Schematic	15.00%	0.83%	$1,650.00	$3,850.00	$0.83	$1.93	22 hrs	2.2 wks	1.7 wks	1.1 wks	0.7 wks	0.6 wks	0.4 wks	0.3 wks	0.2 wks	0.2 wks
Phase 3 - Design Development	20.00%	1.10%	$2,200.00	$6,050.00	$1.10	$3.03	29 hrs	2.9 wks	2.3 wks	1.5 wks	1.0 wks	0.7 wks	0.5 wks	0.4 wks	0.3 wks	0.2 wks
Phase 4 - Construction Documents	45.00%	2.48%	$4,950.00	$11,000.00	$2.48	$5.50	66 hrs	6.6 wks	5.1 wks	3.3 wks	2.2 wks	1.7 wks	1.1 wks	0.8 wks	0.7 wks	0.6 wks
Phase 5 - Bidding and Construction Contract Negotiation	7.00%	0.39%	$770.00	$11,770.00	$0.39	$5.89	10 hrs	1.0 wks	0.8 wks	0.5 wks	0.3 wks	0.3 wks	0.2 wks	0.1 wks	0.1 wks	0.1 wks
Phase 6 - Construction Administration	30.00%	1.65%	$3,300.00	$15,070.00	$1.65	$7.54	44 hrs	4.4 wks	3.4 wks	2.2 wks	1.5 wks	1.1 wks	0.7 wks	0.6 wks	0.4 wks	0.4 wks
	137.00%	7.54%	$15,070.00	$15,070.00	$7.54	$7.54	201 hrs	20.1 wks	15.5 wks	10.0 wks	6.7 wks	5.0 wks	3.3 wks	2.5 wks	2.0 wks	1.7 wks
						5 months	3.9 months	2.5 months	1.7 months	1.3 months	.8 months	.6 months	.5 months	.4 months

## Hourly Rates
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	Cost with Approach (A)	Cost with Approach (B)	Cost with Approach (C)	A Rough Estimated Percentage of Overall Construction Costs	Percentage of Architectural Fees	Cost per SF	Cost per Unit
Architecture				100%	$11,000	$13,000	$15,000	5.50%	100.0%	5.5 $/SF	155 $/SF
Principal	$75/HR	$85/HR	$115/HR
Project Architect	$65/HR	$75/HR	$105/HR
Intern	$55/HR	$65/HR	$95/HR
Structural Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$160/HR	$170/HR	$180/HR
Engineer II	$135/HR	$145/HR	$155/HR
Engineer I	$125/HR	$135/HR	$145/HR
Civil Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$135/HR	$145/HR	$155/HR
Engineer II	$120/HR	$130/HR	$140/HR
Engineer I	$100/HR	$110/HR	$120/HR
Mechanical Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Electrical Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$150/HR	$160/HR	$170/HR
Engineer II	$100/HR	$110/HR	$120/HR
Engineer I	$90/HR	$100/HR	$110/HR
Plumbing Engineer				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Engineer III	$80/HR	$90/HR	$100/HR
Engineer II	$70/HR	$80/HR	$90/HR
Engineer I	$60/HR	$70/HR	$80/HR
Lighting				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
Skill Level 1	$100/HR	$110/HR	$120/HR
Skill Level 2	$90/HR	$100/HR	$110/HR
Skill Level 3	$80/HR	$90/HR	$100/HR

Potential Additional Consultants				0%	$0	$0	$0	0.00%	0.0%	.0 $/SF	$/SF
• Building Envelope Consultant
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				100%	$11,000	$13,000	$15,000	5.5%		5.5 $/SF	154.9 $/SF

## Details
Start	$300
Number of Details	58
Increments	$20

	Cost Per Detail			Total
Approach A	$300	-	$320	$17,400	-	$18,560
Approach B	$340	-	$360	$19,720	-	$20,880
Approach C	$380	-	$400	$22,040	-	$23,200